## Sheet1
Livewest job log
Date enquiry came in | Livewest contact | Address | Works | Appointment date | Completion date | Operative | Gwella job number | Amount | PO Number | Status | Paperwork sent | Comments
2020-08-24 | Mark Atkinson | 5 CRESCENT CLOSE, HAYLE, TR27 4NW | Floor tile removal-36m2 | 25/08/20 pm | 2020-08-25 | Dave Rabey | CGCL071 | 1250.5 | 038334/C02 | Complete | 2020-08-26
2020-08-25 | Mark Atkinson | 73 PENDENNIS ROAD, PENZANCE, TR18 2BE | Floor tile removal and encapsulation | 27/08/20 am | 2020-08-27 | Dave Rabey | CGCL073 | 1404 | 038334/C02 | Complete | 2020-09-01
2020-08-25 | Mark Atkinson | FLATS 1 TO 21 (COMMUNAL) WATERSIDE HOUSE, IVYBRIDGE, PL21 9PF | AIB | 2020-09-17 | 2020-09-17 | Mark Bethell | PGCL052 | 939 | 038334/C02 | Complete | 2020-09-24 | Notification put in 01/09
2020-08-28 | Mark Atkinson | 10 CHAPEL FIELDS, SOUTH BRENT, TQ10 9BS | VFT's and Toilet Seat | 2020-09-01 | 2020-09-01 | Mark Bethell | PGCL049 | 1770 | 038334/C02 | Complete | 2020-09-11
2020-08-28 | Mark Atkinson | 17 SIMMONS WAY, OKEHAMPTON, EX20 1PY | Soil pipe | 2020-09-11 | 2020-09-11 | Matt Peace | PGCL050 | 323 | 038334/C02 | Complete | 2020-09-22
2020-09-02 | Mark Atkinson | 32 Carvedras Court, George Street, Truro, TR1 3UR | Hole drill | 2020-09-04 | 2020-09-04 | Dave Abraham | CGCL094 | 201 | 038334/C02 | Complete | To follow
2020-09-03 | Mark Atkinson | 10 HESSARY TERRACE, PRINCETOWN, YELVERTON, PL20 6RB | Removal of slates and ridges | 2020-09-08 | 2020-09-08 | Matt Peace | PGCL058 | 125 | 038334/C02 | Complete | To follow
2020-09-04 | Mark Atkinson | 3 PARKFIELD CLOSE, BERRY POMEROY, TOTNES, TQ9 5YJ | Screws | 2020-09-08 | 2020-08-08 | Matt Peace | PGCL061 | 263 | 038334/C02 | Complete (see comment) | 2020-09-11 | 08/09/20 took out screws- no replacement screws on site so may need to re-visit
2020-09-04 | Mark Atkinson | 5 CRESCENT CLOSE, HAYLE, TR27 4NW | Floor tiles- Kitchen | 2020-09-07 | 2020-09-07 | Matt Peace | CGCL105 | 175 | 038334/C02 | Complete | 2020-09-11
2020-09-07 | Mark Atkinson | 4 Crescent Close, Hayle, TR17 4NW | Floor tiles - Bedroom 1 (12m2) | 23/09/20 @ 8.30am | 2020-09-23 | Mark Neder | CGCL111 | 329 | 038334/C02 | Complete | 2020-10-06
2020-09-07 | Mark Atkinson | 2 GALLIGAN CLOSE, ST BURYAN, PENZANCE, TR19 6DY | Floor tiles- Shower room | 2020-09-14 | 2020-09-14 | Dave Rabey | CGCL112 | 175 | 038334/C02 | Complete | 2020-09-29
2020-09-11 | Mark Atkinson | 23 St Dunstans Road, Salcombe, TQ8 8AL | Emergency- Window Reveal | 11/09/2020 pm | 2020-09-11 | Andy Purdey | PGCL076 | 671 | 038334/C02 | Complete | 2020-09-22
2020-09-11 | Mark Atkinson | 27 Pendarves Flats, St Clare Street, Penzance, TR18 2PL | Kitchen ceiling | Rebook after Christmas | TBC | TBC | CGCL129 | TBC | 038334/C02 | To be booked
2020-09-14 | Mark Atkinson | 4 Windard Terrace, Sourton, Okehampton, EX20 4HL | Floor tile removal | 2020-09-30 | 2020-09-30 | Mark Bethell | PGCL079 | 220 | 038334/C02 | Complete | 2020-10-08 | removal of broken tiles complete, attend separately to undertake removal of all tiles
2020-09-14 | Mark Atkinson | 16 Moyses Meadow, Okehampton, EX20 1JY | Lounge ceiling repair | 2020-09-30 | 2020-09-30 | Mark Bethell | PGCL078 | 260 | 038334/C02 | Complete | 2020-10-08
2020-09-14 | Mark Atkinson | 35 Yeo Park, Yealmton, PL8 2LP | Kitchen ceiling collapse | 2020-09-14 | 2020-09-14 | Mark Bethell | PGCL080 | 337 | 038334/C02 | Complete | 2020-09-15 | waste note to follow
2020-09-16 | Mark Atkinson | 3 Treveneth Place, Newlyn, Penzance,TR18 5NQ | AC Debris | 2020-09-17 | 2020-09-17 | Matt Peace | CGCL147 | 257 | 038334/C02 | Complete | 18/09/2020/ 29/09/20
2020-09-17 | Mark Atkinson | 5 Queensway, Hayle,TR27 4NJ | AC Pipe in shed | 2020-09-17 | 2020-09-17 | Matt Peace | CGCL148 | 123 | 038334/C02 | Complete | 18/09/2020/ 29/09/20
2020-09-17 | Mark Atkinson | 9 Hurrell Court, Hurrell Road, Kingsbridge, TQ7 1HT | Hole drill | 02/10/2020 @ 08:30 | 2020-10-02 | Matt Peace | PGCL090 | 263 | 038334/C02 | Complete | 2020-10-08
2020-09-18 | Mark Atkinson | 40 Roydon Lane, Launceston, PL15 8NG | Flaking TC | Cancelled as no answer from the tenant |  |  | CGCL156 |  | 039684/C02 | Cancelled |  | No answer from tenant and not there on first visit
2020-09-18 | Mark Atkinson | 1 Parkfield Walk, Thurlestone, Kingsbridge, TQ7 3TL | AIB removal store ceiling and encapsulation of soffits and porch ceiling | 2020-10-19 | 2020-10-19 | Mark Bethell | PGCL089 | 1707 | 038334/C02 | Complete | 2020-11-09
2020-09-22 | Graham Last | 7 Tremorva, Hayle, TR27 4JZ | Floor tiles throughout (39m2) | 24/09/20 12.00pm | 2020-09-24 | Dave Rabey | CGCL166 | 1043 | 038334/C02 | Complete | 2020-09-29
2020-09-22 | Graham Last | 79-85 Odds, Pendennis Road (Comm), Penzance, TR18 2BE | Hole drills for light fitting | 07/10/20 @ 8.30am | 2020-10-07 | Wayne T | CGCL167 | 201 | 039684/C02 | Complete | 2020-10-21
2020-09-22 | Mark Atkinson | 17 Weatherdon Drive, Ivybridge, PL21 0DD | AIB Panel to floor | 23/10/20 11.15am | 2020-10-23 | Mark Bethell | PGCL093 | 1547 | 038334/C02 | Complete | 2020-11-09
2020-09-22 | Mark Atkinson | 23 Weatherdon Drive, Ivybridge, PL21 0DD | AIB Panel to floor and floor tiles | 2020-10-22 | 2020-10-22 | Mark Bethell | PGCL094 | 1722 | 038334/C02 | Complete | 2020-11-09
2020-09-22 | Graham Last | 1 Victoria Court, Totnes, TQ9 5TR | Flaky ceiling repairs | 20/10/20 @ 8.30am | 2020-10-20 | Mark Bethell | PGCL095 | 468 | 038334/C02 | Complete | 2020-11-09
2020-09-22 | Graham Last | 31 Bucktor Park, Tavistock, PL19 8EP | Floor tiles | 2020-10-09 | 2020-10-09 | Andy Purdey | PGCL096 | 175 | 039684/C02 | Complete |  | Due to attend 20/10 but tenant removed tiles herself- AP attended 09/10 to ensure area safe and clean up
2020-09-29 | Mark Atkinson | 17 Pen Tye, Gwinear, Hayle, TR17 5HL | Scrape artex | 01/10/20 @ 10.30am and 30/10/20 | 01/10/2020 and 30/10/20 | Matt Peace | CGCL186 | 260 | 039684/C02 | Complete | 2020-10-08
2020-09-29 | Mark Atkinson | CRESCENT COURT (COMM), TOWNSTAL CRESCENT, TOWNSTAL, DARTMOUTH, TQ6 9LU | Floor tiles | 01/10/20 @ 4pm | 2020-10-01 | Mark Bethell | PGCL113 | 175 | 039684/C02 | Complete | 2020-10-08
2020-09-30 | Mark Atkinson | GRND FLAT; 22 WYNDHAM ST WEST, STONEHOUSE, PLYMOUTH, PL1 5ER | Emergency- AIB disturbance | 2020-09-30 | 2020-09-30 | Mark Bethell | PGCL116 | 583 | 039684/C02 | Complete | 2020-10-08
2020-09-30 | Mark Atkinson | GRND FLAT; 22 WYNDHAM ST WEST, STONEHOUSE, PLYMOUTH, PL1 5ER | Removal and re-instatement | 18/12/20 (Livewest telling tenant we need access) | TBC | Mark Bethell | PGCL132 | 1840 | 039833/C02 | Booked |  | Sent letter to confirm appointment- 26/11/20
2020-10-01 | Mark Atkinson | Ground Flat, 53 Cecil Street, Stonehouse, Plymouth, PL1 5HP | AIB removal and re-instatement | cancelled- instruction from Livewest | TBC | Mark Bethell | PGCL119 | 1840 | 039684/C02 | Cancelled |  | No key/no power on site- re-notify- 20/10
2020-10-01 | Mark Atkinson | 4 Windard Terrace, Sourton, Okehampton, EX20 4HL | Floor tile removal (whole kitchen) 10 m2 | 2020-10-05 | 2020-10-05 | Matt Peace | PGCL131 | 290 | 039684/C02 | Complete | 2020-10-08
2020-10-02 | Mark Atkinson | 57 Lafrowda Close, St Just, Penzance, TR19 7JA | Drill hole for smoke alarm | 12/10/20 @ 8am | 2020-10-12 | Dave Rabey | CGCL200 | 263 | 039684/C02 | Complete | 2020-10-22
2020-10-05 | Mark Atkinson | 11 Island View, Thurlestone, Kingsbridge, TQ7 3NH | Coal bunker door and soffit encapsulation | 2020-10-16 | 16/10/20 and 17/10/2020 | Andy Purdey | PGCL129 | 614 | 039684/C02 | Complete |  | Coal bunker completed, revisit 17/10/2020 to complete soffit encapsulate
2020-10-06 | Mark Atkinson | 10 TRELOWETH CLOSE, ST ERTH, HAYLE, TR27 6JR | Floor tiles- 38m2 (kitchen and bathroom) | 08/10/20 am | 2020-10-08 | Matt Brewer | CGCL210 | 1419.5 | 039684/C02 | Complete | 2020-10-21
2020-10-07 | Mark Atkinson | 28 Stott Close, Efford, Plymouth, PL3 6HA | Ceiling removal | 30/11/20 first thing | 2020-11-30 | Neil Stocks | PGCL134 | 641 | 041575/C02 | Complete | 2020-12-11
2020-10-08 | Graham Last | 2 Gillards, Bishops Hull, Taunton, TA1 5HH | Floor tiles | 15/10/20 AM | 2020-10-16 | Andy Purdey | PGCL135 | 175 | 039684/C02 | Complete | 2020-11-09 | Project completed on 16/10/2020 due to emergency on 15/10/2020
2020-10-08 | Graham Last | GROUND FLAT; 18 WYNDHAM SQUARE,STONEHOUSE, PLYMOUTH PL1 5EG | Emergency- hole on floor | 2020-10-08 | 2020-10-09 | Dave Rabey | CGCL223 | 268.5 | 039684/C02 | Complete | 2020-10-21
2020-10-13 | Mark Atkinson | 51 Lafrowda Close, St. Just, Penzance, TR19 7JA | Damaged textured coating | 2020-10-19 | 2020-10-19 | Matt Peace | CGCL258 | 330 | 039684/C02 | Complete | 2020-11-02
2020-10-13 | Mark Atkinson | Flat 8, Courtenal House, Honicknowle Green, Plymouth, PL5 3PL | Drilling TC for smoke detectors | 2020-11-24 | 2020-11-24 | Neil Stocks | PGCL153 | 263 | 040472/C02 | Complete | 2020-12-11
2020-10-13 | Mark Atkinson | 35 Trewarton Road, Penryn, TR10 8JB | Remove hallway TC ceiling | 2020-10-20 | 2020-10-20 | Matt Peace | CGCL259 | 470 | 039684/C02 | Complete | 2020-11-02
2020-10-14 | Mark Atkinson | 44 Moyses Meadow, Okehampton, EX20 1JY | Insulating Board panel | 2020-11-25 | 2020-11-25 | Mark Bethell | PGCL154 | 1173 | 039684/C02 | Complete |  | Attended on 09/11 but DCU went wrong- rebooked for 25th nov
2020-10-16 | Mark Atkinson | Garage, 8 Boltern Road, Marazion, TR17 0DL | AC roofing removal- 18m2 | 2020-11-11 | 2020-11-11 | Kevin Webb | CGCL260 | 637.65 | 040473/C02 | Complete | 2020-12-08 | WCMS contacted, awaiting date when they can attend to replace
2020-10-16 | Mark Atkinson | 54 Weatherdon Drive, Ivybridge, PL21 0DD | AIB panel | 2020-12-16 | TBC | Ashley Groves | PGCL155 | 1547 | 039684/C02 | Booked
2020-10-19 | Mark Atkinson | 23 St Dunstans Road, Salcombe, TQ8 8AL | Window reveals- except kitchen | 2020-11-09 | 2020-11-09 | Chris Joyce | PGCL158 | 894 | 040472/C02 | Complete | 2020-11-18
2020-10-20 | Mark Atkinson | 1A Butterlake, Marldon, Paignton, TQ3 1SN | Fire place and water tank | 2020-10-22 | 2020-10-22 | Ashley Groves | PGCL163 | 422 | 039684/C02 | Complete
2020-10-21 | Mark Atkinson | 13 Dukes Road, Totnes, TQ9 5AY | AIB Forming shelf | Had booked 9th Dec- tenant has got to self isolate- re book after Christmas | TBC | TBC | PGCL165 | 913 | 041575/C02 | To be booked |  | Sent letter to confirm appointment- 26/11/20
2020-10-22 | Mark Atkinson | 2 Arundell Close, Lifton, PL16 0DP | Encapsulation in bathroom | 26/10/20 @ 1pm | 2020-10-26 | Matt Peace | CGCL287 | 230 | 040473/C02 | Complete | 2020-11-09
2020-10-22 | Mark Atkinson | 6 Foxfield Close, Laira, Plymouth, PL3 6DF | AIB Door header and re-instatement | Try again after Christmas to book as no repsonse previously | TBC | Ashley Groves | PGCL170 | 1580 | 041225/C02 | Waiting on tenant |  | Sent letter to confirm appointment- 26/11/20
2020-10-26 | Mark Atkinson | 55 TRELOWETH CLOSE, ST ERTH, HAYLE, TR27 6JR | Floor tiles in kitchen- 14m2- 3 layers | 11/11/20 @ 2pm | 2020-11-11 | Kevin Webb | CGCL299 | 500 | 040473/C02 | Complete | 2020-12-08
2020-10-26 | Mark Atkinson | 10 CUSTOM HOUSE COURT, PENZANCE, TR18 4AT | Floor tiles in kitchen- 4m2- 4 layers | 11/11/20 @ 9am and 12/11/20 | 2020-11-12 | Kevin Webb | CGCL300 | 280 | 040473/C02 | Complete | 2020-12-08
2020-10-26 | Mark Atkinson | 18 PEN AN GWEL, ST IVES, TR26 1DL | Floor tiles in kitchen | 07/12/20 @ 9am | 2020-12-07 | Matt Peace | CGCL301 | 472 | 040473/C02 | Complete
2020-10-27 | Mark Atkinson | 14 Bens Close, Galmpton, Kingsbridge, TQ7 3EZ | Emergency attendance plus return visit to remove fireplace and watertank | 27/10/20 and 31/10/20 | 2020-10-31 | Ashley Groves | PGCL186 | 894 | 040472/C02 | Complete | 2020-11-16
2020-10-28 | Mark Atkinson | 32 Churchill Road, Bideford, EX39 4HG | Fittings and cupboard | 29/10/20 @ 11.30am | 2020-10-29 | Matt Peace | CGCL305 | 263 | 040473/C02 | Complete | 2020-11-09
2020-10-29 | Mark Atkinson | FLAT 17; ROOKWOOD HOUSE, ROOKWOOD CLOSE, HONITON, EX14 1BP | AIB and reinstatement | 2020-11-30 | 2020-11-30 | Nathan Groves | PGCL195 | 1580 | 041222/C02 | Complete | 2020-12-11
2020-10-29 | Mark Atkinson | 5 Furze Road, Berry Pomeroy, Totnes, TQ9 5YE | AIB | No response- works cancelled | TBC | TBC | PGCL199 | 913 | 041575/C02 | Cancelled
2020-10-29 | Mark Atkinson | 3 Mill Meadow, Ivybridge, PL21 0AN | Hole drill | 2020-11-09 | 2020-11-09 | Nathan Groves | PGCL201 | 201 | 040472/C02 | Complete
2020-10-29 | Mark Atkinson | 4 Jack Stephens Estate, Penzance, TR18 2QE | Emergency attendance- ceiling | Waiting on DWT to confirm when they can attend with us after xmas | 2020-10-29 | Mark Neder | CGCL319 | £211 for call out only | 040473/C02 | Emergency attend- Complete Whole ceiling removal- To be booked
2020-10-29 | Mark Atkinson | 27 Steer Point Road, Brixton, Plymouth, PL8 2BN | Encapsulation of AIB | 2021-01-08 | TBC | Neil Stocks | PGCL202 | 589 | 041575/C02 | Booked
2020-10-29 | Mark Atkinson | 139 Brentford Avenue, Whitleigh, Plymouth, PL5 4HE | Encapsulation of AIB | Trying to book for 18th Dec- left VM (8th) | TBC | TBC | PGCL203 | 821 | 041575/C02 | Waiting on tenant
2020-10-30 | Graham Last | 42-48 Cox Tor Road, Tavistock, PL19 9JG | Emergency ceiling collapse | 2020-11-23 | 2020-11-23 | Mark Bethell | PGCL208 | 1494 | 040472/C02 | Complete | 2020-12-11 | Sent letter to confirm appointment- 26/11/20
2020-10-30 | Graham Last | 42-48 Cox Tor Road, Tavistock, PL19 9JG | 2nd visit | 2020-12-11 | 2020-12-11 | Mark Bethell | PGCL301 | 939 | 041575/C02 | Complete
2020-11-05 | Graham Last | 29 Collapark, Totnes, Devon, TQ9 5LN | Asbestos board collection | 2020-11-12 | 2020-11-12 | Mark Bethell | PGCL222 | 257 | 040472/C02 | Complete
2020-11-06 | Graham Last | 22 Riverdale, Harbertonford, Totnes, TQ9 7TJ | Asbestos board collection | 2020-11-06 | 2020-11-06 | Andy Purdey | PGCL225 | 257 | 040472/C02 | Complete
2020-11-06 | Graham Last | 39 Trelawney Avenue, St Ives, TR16 1AS | Sheet collection- 1m2 | 11/11/20 2pm | 2020-11-11 | Kevin Webb | CGCL347 | 257 | 040473/C02 | Complete | 2020-12-08
2020-11-06 | Graham Last | Holdsworth House (Comm), Higher Street, Dartmouth, TQ6 9RP | Ceiling and debris | 2020-11-10 | 2020-11-10 | Chris Joyce | PGCL228 | 400 | 040472/C02 | Complete
2020-11-09 | Mark Atkinson | 53 Sedgemoor Road, Bath, BA2 5PL | Ceiling | 2020-11-09 | 2020-11-09 | Ashley Groves | PGCL230 | 732 | 040472/C02 | Complete | 2020-12-11
2020-11-10 | Mark Atkinson | 89 Bifield Road, Stockwood, Bristol, BS14 8TT | Ceiling repairs | 12/11/20 4pm | 2020-11-12 | Chris Joyce | PGCL237 | 400 | 040472/C02 | Complete
2020-11-11 | Mark Atkinson | 43 & 44 Pathfields, Bridgetown, Totnes, TQ9 5TZ | Downpipes | 2020-11-24 | 2020-11-24 | Neil Stocks | PGCL242 | 674 | 040472/C02 | Complete
2020-01-11 | Mark Atkinson | 20 Jubilee Close, Townstal, Dartmouth, TQ6 9LY | Ceiling repairs | 11/11/2020 @ 6.30pm | 2020-11-11 | Nathan Groves | PGCL240 | 300 | 040472/C02 | Complete
2020-11-11 | Mark Atkinson | 38 St Johns Road, Horrabridge, Yelverton, PL20 7SX | Ceiling removal | 2020-11-14 | 2020-11-14 | Chris Joyce | PGCL245 | 729 | 041089/C02 | Complete
2020-11-16 | Mark Atkinson | Flat 3, Higherside, Dartmouth,TQ6 9RD | Collection of ironing board | 2020-11-17 | 2020-11-17 | Mark Bethell | PGCL252 | 264 | 040472/C02 | Complete
2020-11-18 | Graham Last | 7 Courtenay Road, Okehampton, EX20 1PZ | Floor tiles | 20/11/2020 @ 12pm | 2020-11-20 | Neil Stocks | PGCL257 | 175 | 040472/C02 | Complete | 2020-12-11
2020-11-19 | Mark Atkinson | 1-6 Parkfield Walk, Kingsbridge, TQ7 3TL | Porch | Schedule in the new year | TBC | TBC | PGCL267 | 8535 | will need an individual PO | To be booked
2020-11-19 | Mark Atkinson | 136 Tamar Avenue, Greenlands, Tavistock, PL19 9JA | Floor tiles | 2020-11-23 | 2020-11-23 | Neil Stocks | PGCL269 | 290 | 040472/C02 | Complete
2020-11-19 | Mark Atkinson | Garage 29, Simmons Way, OKEHAMPTON, EX20 1PY | Garage removal | 2021-01-04 | TBC | TBC | CGCL426 | 1790 | 041577/C02 | Booked
2020-11-20 | Mark Atkinson | 37 Clover Way, Highbridge, Somerset, TA9 3LL | Coving and floor tiles | 2020-11-27 | 2020-11-27 | Mark Bethell | PGCL276 | 2000 | 041371/C02 | Complete | 2020-12-11
2020-11-20 | Mark Atkinson | 1st Flat, 286 North Rd West, Stonehouse, Plymouth, PL1 5DQ | Asbestos slate | 2020-11-25 | 2020-11-25 | Neil Stocks | PGCL268 | 175 | 040472/C02 | Complete | 2020-12-11
2020-11-24 | Mark Atkinson | 34 Hayes Close, Berry Pomeroy, Totnes, TQ9 5YB | Shelf with vinyl lining | 2020-11-27 | 2020-11-27 | Neil Stocks | PGCL285 | 175 | 040472/C02 | Complete
2020-11-25 | Mark Atkinson | 26 Manor Close, Ivybridge, PL21 9BQ | Floor tiles 12 sq | 2020-11-30 | 2020-11-30 | Neil Stocks | PGCL288 | 290 | 041575/C02 | Complete | 2020-12-11
2020-11-25 | Mark Atkinson | 72 Thornpark Road, St Austell, PL25 4DP | Floor tiles | 2020-11-26 | 2020-11-26 | Matt Peace | CGCL417 | 175 | 040473/C02 | Complete | 2020-12-07
2020-11-25 | Mark Atkinson | 33 Foxfield Close, Laira, Plymouth, PL3 6DF | Hole drill | Waiting on livewest | TBC | TBC | PGCL290 | 201 | 041575/C02 | To be booked
2020-11-26 | Graham Last | 1-6 Carvedras Court (Comm), George Street, Truro, TR1 3UR | TC Ceiling | 30/11/20 @ 12.30- tried to attend but artex is on concrete not plasterboard- just charge for aborted visit only as not going ahead with works | 2020-11-30 | Dave Rabey | CGCL419 | 78 | 040473/C02 | Complete | No paperwork as aborted visit only
2020-11-26 | Mark Atkinson | 42 Foxfield Close, Laira, Plymouth, PL3 6DF | Hole drill | 07/12/20 @10am | 2020-12-07 | Martyn Thorpe | PGCL295 | 201 | 041575/C02 | Complete | 2020-12-11
2020-11-26 | Mark Atkinson | 18 Falklands Rise, Minehead, TA24 8UA | Scrape artex | 01/12/20 @ 10am | 2020-12-01 | Martyn Thorpe | PGCL296 | 370 | 041575/C02 | Complete | 2020-12-11
2020-11-26 | Mark Atkinson | 38 Furze Park, Barne Barton, Plymouth, PL5 1BW | Emergency- Ceiling | 2020-11-26 | 2020-11-26 | Neil Stocks | PGCL297 | 610 | 041575/C02 | Complete
2020-11-26 | Mark Atkinson | 8 Pendragon Crescent, Newquay, TR7 2SY | Floor tiles | 07/12/20 @ 12pm | 2020-12-07 | Matt Peace | CGCL421 | 472 | 040473/C02 | Complete
2020-12-01 | Mark Atkinson | 16 Essex Street, Stonehouse, Plymouth, PL1 5HB | TC on concrete removal | Originally booked for-14/12/2020- postponed until new year- wait to hear from Livewest | TBC | Nathan Groves | PGCL308 | 729 | 041575/C02 | To be booked
2020-12-02 | Mark Atkinson | 60 Gladstone Street, Taunton, Somerset, TA2 6LY | Floor tiles | 2020-12-07 | 2020-12-07 | Mark Bethell | PGCL309 | 1995.5 | 041761/C02 | Complete
2020-12-07 | Mark Atkinson | 20 Bowringsleigh Place, Kingsbridge, TQ7 1RB | Floor tiles and AIB | 2020-12-10 | 2020-12-10 | Mark Bethell | PGCL337 | 343.5 | 041575/C02 | Complete
2020-12-08 | Mark Atkinson | 30 Moor View, Hatherleigh, Okehampton, EX20 3LB | Scrape and seal of TC | 2020-12-11 | 2020-12-11 | Martyn Thorpe | PGCL338 | 477 | 041575/C02 | Complete
2020-12-08 | Mark Atkinson | 9 Ark Royal Close, Barne Barton, Plymouth, PL5 1EZ | Emergency ceiling collapse | 2020-12-08 | 2020-12-08 | Andy Purdey and Martyn Thorpe | PGCL339 | 300 | 041575/C02 | Complete | 2020-12-11
2020-12-08 | Mark Atkinson | 64 St Clements Close, Truro, TR1 1PA | Encapsulate holes | 11/12/20 @ 8.30am | 2020-12-11 | Dave Rabey | CGCL448 | 98 | 040473/C02 | Complete
2020-12-08 | Mark Atkinson | 59 Treveglos, Hayle, TR27 4LA | Collection | 2020-12-09 | 2020-12-09 | Dave Abraham | CGCL449 | 91 | 040473/C02 | Complete
2020-12-08 | Mark Atkinson | 16 Lafrowda Close, St Just, Penzance, TR19 7HZ | Hole drill | 08/01/21 @ 8.30am | TBC | Matt Peace | CGCL450 | TBC | 040473/C02 | Booked
2020-12-08 | Mark Atkinson | Holdsworth House (Comm), Higher Street, Dartmouth, TQ6 9RP | Ceiling removal | 15/12/20 evening | TBC | Nathan Groves | PGCL342 | TBC | need new number | To be booked
2020-12-09 | Mark Atkinson | 8 Fillace Park, Horrabridge, Yelverton, PL20 7TB | TC removal and encapsulation | 2020-12-17 | TBC | Neil Stocks | PGCL344 | TBC | need new number | Booked
2020-12-09 | Mark Atkinson | FLATS 1 TO 21 (COMMUNAL) WATERSIDE HOUSE, IVYBRIDGE, PL21 9PF | AIB | AP- visiting to scope 11/12 | TBC |  | PGCL347 | TBC | need new number | To be booked
2020-12-11 | Karl Carver | 20 Bowringsleigh Place, Kingsbridge, TQ7 1RB | Hole drill | 2020-12-15 | TBC |  | PGCL351 | TBC | need new number | Booked
2020-12-11 | Graham Last | 29 The Ropewalk, Penzance, TR18 4QN | Collection of asbestos sheets | 2020-12-14 | TBC | TBC | CGCL459 | TBC | 040473/C02 | Booked
Note on E78: Evie Hidderley: 1 Parkfield Walk – Ms J Caswell - 01548 560886 ALREADY DONE? 2 Parkfield Walk – Mrs V Vernon – 01548 560805 3 Parkfield Walk – Mr & Mrs Williams – 01548 561045 / 07534 981386 4 Parkfield Walk – Mr & Mrs Webb – 01548 562489 / 07717 754152 5 Parkfield Walk – Mr & Mrs French – 07538 950351 6 Parkfield Walk – Mrs Glanville – 07935 757583

## Sheet2
PO LOG
41575/C02
PGCL134 | 641
PGCL165 | 913
PGCL199 | 913
PGCL202 | 589
PGCL203 | 821
PGCL301 | 939
PGCL288 | 290
PGCL290 | 201
PGCL295 | 201
PGCL296 | 370
PGCL297 | 610
PGCL308 | 729
PGCL339 | 300
PGCL338 | 477
PGCL337 | 343.5
8337.5
040473/C02
CGCL260 | 637.65
CGCL287 | 230
CGCL299 | 500
CGCL300 | 280
CGCL301 | 472
CGCL305 | 263
CGCL319 | 211
CGCL347 | 257
CGCL417 | 175
CGCL419 | 78
CGCL421 | 472
CGCL448
CGCL449
CGCL450
CGCL459
3575.65