## FABRIC (hidden)
. | LOT 1 | BUILDING FABRIC | MONTHLY MAINTENANCE CONTRACT MEETINGS
| DATE | 2017-05-30
| ATTENDEES | Phil McMullan (WC) Maureen Wells (WC) Tom Somerville (Kier) Pete Wort (Kier) Greg Jones (Kier) Vincent Albano (WC)
| APOLOGIES | Paul Bramhall (Kier) Liza Gordon (WC)
| MT | Liza Gordon
DATE Example 26.4.16 | AGENDA CATEGORY | SITE / LOCATION / GENERAL | TITLE / BRIEF DESCRIPTION | COMMENTS | PERSON TO ACTION | DATE TO BE ACTIONED BY | STATUS
.0. H&S
.1. REACTIVE
.2. SUBMISSION
.3. EARLY WARNING
.4. KPI's
.5. CONTRACTUAL
.6. ENERGY
.7. CAPITAL WORKS
.8. SITE CHANGES
.9. COMPLAINTS
10. COMPLIMENTS
26.4.16 | .0. H&S | Site as required | If any H/S issues identified, these can also be reported by the Delivery Managers via e-mail | Once Concerto goes live any issues can be input straight onto the system | Phil McMullan | 24.5.16 | Closed
26.4.16 | .0. H&S | Kingsbury Square | Concerns were raised with regards to High Risk Sites | 2 engineers to attend until further notice. | Tom Somerville | 24.5.16 | Closed
26.4.16 | .0. H&S | Kingsbury Square | Concerns regarding OOH attendance | Advised Keyline Security could assist. |  | 24.5.16 | Closed
26.4.16 | .0. H&S | Traveller Sites | Contractors Site Safety | Reports any issues to WC which can be passed to Traveller Liaison Office. | Tom Somerville | 24.5.16 | Closed
26.4.16 | .0. H&S | Traveller Sites | Residents interfering when contractor trying to carry out electrical works | Incident closed however any further issues should be reported to WC which can be passed to Traveller Liaison Office | Tom Somerville | 24.5.16 | Closed
26.4.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | Fencing was put in place as instructed however Engineer still had concerns in relation to on going site operations Reported To Jenny Rowe who will monitor the situation | Jenny Rowe | 24.5.16 | Closed
26.4.16 | .0. H&S | Farms | Full Risk Assessment to be carried out (Farms only for working in area of cess pits etc.) | Generic Risk Assessment carried out by Kier | P Wort | 24.5.16 | Closed
26.4.16 | .0. H&S | Toolbox Training | New employees | Inductions carried out | P Wort | April | Closed
26.4.16 | .0. H&S | Toolbox Training | DBS for all staff | PW advised staff without DBS are pairing up with DBS holders. PW enquired if school to be updated on DBS procedures | P Wort | 24.5.16 | Closed
26.4.16 | .1. REACTIVE | All Sites | Reactive orders to be monitored when placed by WC Helpdesk as concerns raised how many 2hrs 4hrs and 24hrs are being raised | WC Helpdesk to be advised | Phil Mc | 24.5.16 | Closed
26.4.16 | .1. REACTIVE | All Sites | Pre-measure clarification | Phil to liaise with Ian Gillard if wording can be changed when orders placed so that Kier staff can recognise as Fabric requires premeasure M/E budget. | Phil Mc | 24.5.16 | Closed
26.4.16 | .1. REACTIVE | All Sites | When premeasure requested - timescale on return doc for approval. | Timescale can be between 14 - 28 days. Phil to discuss formal instruction. | Phil Mc | 21.6.16 | Closed
26.4.16 | .2. SUBMISSION | All sites | Reactive submission to be sent to Technical Officers - To be returned to for approval within 3 days | Kevin to distribute Submission to Tec Officers to view and agree | Kevin Butcher | Closed | Closed
26.4.16 | .2. SUBMISSION | All sites | Submission time scales | (Submission to be returned within 2 weeks) | Mo Wells | 24.5.16 | Closed
26.4.16 | .3. EARLY WARNING | General | Greg Jones raised early warning due to documentation impact not being loaded onto Concerto | Ian Gillard to update | Ian Gillard | 24.5.16 | Closed
26.4.16 | .4. KPI's | General | KPI's to be sent before next meeting so any issues can be raised. | To be sent to Phil McMullan | Phil Mc | 24.5.16 | Closed
24.5.16 | .4. KPI's | General | KPI's to be sent to Phil McMullan to discuss process. | Phil and Paul to discuss in separate meeting | Phil/Paul | 21.6.16 | Closed
26.4.16 | .5. CONTRACTUAL | All site | Day to day issues to be raised when required to Phil McMullan or Delivery Managers | To be e-mailed to Phil McMullan | Phil Mc | 24.5.16 | Closed
24.5.16 | .5. CONTRACTUAL | General | PB to advise process for submitting KPIs to PM | PB to meet with PM and agree process | PM / PB | 24.5.16 | Closed
26.4.16 | .5. CONTRACTUAL | All site | Kevin Butcher. Phil McMullan requested a list of sub- contractors used by Kier | Kevin/ Phil to advise if sub-contractors to be removed from list. | Tom Somerville/ Pete Wort | 21.6.16 | Closed
26.4.16 | .6. ENERGY | General | Nothing to report | No Action |  | Closed | Closed
26.4.16 | .8. SITE CHANGES | Site | Kier to be informed of any changes to site e.g.. voids, or no longer WC responsibility | Mo/Liza to update accordingly | Mo/Liza | Closed | Closed
26.4.16 | .9. COMPLAINTS | General | Non received | No action required |  | 26.4.16 | Closed
26.4.16 | 10. COMPLIMENTS | Chirton Primary School | Iwan Van Der Berg compliment to Dave Gibson on keeping him informed on any issues from the snagging list on the mobile | Kier to pass comments | Paul Bramhall | 26.4.16 | Closed
26.4.16 | .7. CAPITAL WORKS | All sites | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA | Phil to liaise with Theo Binley on correct procedures. Theo advised Greg to have only one generic e-mail address/name when making any enquires. Greg to speak to Kier IT. | PM | Closed | Closed
24.5.16 | .0. H&S | Toolbox Training | DBS for all staff | Pete Wort advised only 1 member of staff still requires DBS clearance. | Pete Wort | 24.6.16 | Closed
24.5.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | Fencing has been erected, still had concerns in relation to on going site operations. Kier has advised that a structural engineer may need to attend site to access and advise, Jenny Rowe to be advised of the situation. | Jenny Rowe | 22.11.16 | Closed
24.5.16 | .0. H&S | All Sites | Risk Assessments | Risk Assessment carried out by Kier - still ongoing | PW | NOTE | Closed
24.5.16 | .1. REACTIVE | All Sites | Pre-measure clarification | Phil to liaise with Ian Gillard to suggest another 'C' category can be added to GVAs orders so that Kier staff can recognise if a premeasure or budget costings required. Ian agreed and will add a new category, | Ian Gillard | 21.6.16 | Closed
24.5.16 | .1. REACTIVE | Schools Site | School works exceeding threshold | To clarify orders over the value to £500.00 to be approved by the school. Phil advised this to be added on to the agenda for the purposed open day on the 06/07/2016 for school that have re-joined the compliance scheme. | Phil Mc | 21.6.16 | Closed
24.5.16 | .2. SUBMISSION | All sites | Reactive submission to be sent to Technical Officers - | Reactive submission to be sent to Technical Officers via Kevin Butcher. To be returned to for approval within 3 days | Kevin Butcher | 21.6.16 | Closed
24.5.16 | .2. SUBMISSION | All sites | PPM submission to be sent to Maureen Wells | Corresponding documentation to be located on QFM | Mo Wells | 21.6.16 | Closed
24.5.16 | .3. EARLY WARNING | General | No action taken | Non Issued |  |  | Closed
24.5.16 | .5. CONTRACTUAL | All site | Kevin Butcher. Phil McMullan requested a list of sub- contractors used by Kier | Pete Wort advised list is now near completion, to then be forwarded to Kevin and Phil. | Pete Wort | 21.6.16 | Closed
24.5.16 | .5. CONTRACTUAL | All site | Pre- measure works. | Scope of planned works to have relevant documents, e.g. drawings. Kier also advised that the corresponding job spec. to be signed off by Technical Office before GVAs orders placed, so that there are no miss- understanding between contactor and client. Phil to liaise with Technical Officers. To also be discussed further at the quarterly contractors meeting. | Phil MC | 21.6.16 | Closed
24.5.16 | .6. ENERGY | General | Energy / carbon reduction incentive | Kier new vans are energy efficient are also fitted with tracking devices. | Greg Jones | Closed | Closed
24.5.16 | .7. CAPITAL WORKS | All sites | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA works still via Consultants re Mike Canepari. | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA works still via Consultants re Mike Canepari MTC works allocated direct form Technical Officers. . To also be discussed further at the quarterly contractors meeting. | PM | Closed | Closed
24.5.16 | .8. SITE CHANGES | Site | Site changes | Pennyfarthing House, Salisbury - no longer WC property from the 01/07/2016.Kevin to liaise with developer if site to be decommissioned of all services. Calne Leisure Centre to be added to list from 21/06/2016 | Kevin/Phil | Closed | Closed
24.5.16 | .9. COMPLAINTS | General | Non received | No action required |  | 24.5.16 | Closed
24.5.16 | 10. COMPLIMENTS |  | Kevin stated he was pleased with the mobilisation process and it success. |  | Kevin Butcher | 24.5.16 | Closed
21.6.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advised 3 member of staff still require DBS clearance. | P Bramhall | Closed | Closed
26.6.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advise 1 staff member to be finalised on DBS | PB / PM | 22.8.16 | Closed
21.6.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | Fencing around building, still ongoing. Kier has advised that a structural engineer may need to attend site to access and advise, Meeting with Jenny Rowe or be arranged. | Jenny Rowe/Phil McMullan/Dave Collier | 22.8.16 | Closed
26.7.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | UPDATE. Kier Structural Engineer to provide report | PW | 5.8.16 | Closed
21.6.16 | .0. H&S | Risk Assessments | Kier Staff | Toolbox training for staff on Slip, Trip, Falls. Dog Bites. Drink, Drugs. | Greg Jones | Closed | Closed
26.7.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side | Staff meeting | Closed | Closed
21.6.16 | .1. REACTIVE | All Sites | Pre-measure clarification | Phil to liaise with Ian Gillard to confirm if 'C' category or budget costings has been added to GVA's and relevant parties informed e.g.. Helpdesk staff. | IG/PM | 23.8.16 | Closed
21.6.16 | .1. REACTIVE | Schools Site | School works exceeding threshold | To clarify orders over the value to £500.00 to be approved by the school. Phil advised this to be added on to the agenda for the School open day on the 06/07/2016. | PM | 14.9.16 | Closed
21.6.16 | .1. REACTIVE | Schools Site | Schools requesting costing | John Bolton advised when extra works are required at schools they are requesting costings prior to the works being carried out irrelevant of the sizes of the works . Issue to be raised at the 'Open Day' | Phil Mc | 06.7.16 | Closed
21.6.16 | .1. REACTIVE | All site | Issue with out standing works and contractor arriving at site without making appointments. | Phil had received several e-mail from Technical Officers, Delivery Managers and Estates Officers to report that contractors were arriving on site without making appointments, other issues reported was O/S works still not completed. One of concern reported by Kez Hutchens, Hilmarton School fence repairs, due to parts being required, the children were not protected from the neighbouring field allowing cows to enter the school area. Greg requested that all correspondence be sent to him so that that he could investigate further. Greg also requested any issues be sent to him prior to the contractors meeting so that he could advise accordingly. Greg to also look into how Kier QS's are receiving information so that these kind of issues can be eliminated | Phil Mc | Closed | Closed
21.6.16 | .1. REACTIVE | Sites as required | Summer Holiday works | Greg advised Kier were now in partnership with contractors so that resources would be available for the required summer holiday works. | Greg Jones | Closed | Closed
21.6.16 | .2. SUBMISSION | All sites | SAP purchase orders. | Kier advised these are separate from GVA's order no. and should not be added to the submission. | Kier | 20.12.16 | Closed
26.7.16 | .2. SUBMISSION | General | Monthly Submission and cross service sectors | PM identified that there were still issues whereby works were being allocated to the incorrect lots on the order from the helpdesk. PM to provide further help and guidance. | PM | 5.8.16 | Closed
21.6.16 | .3. EARLY WARNING | General | No action taken | Non Issued |  |  | Closed
21.6.16 | .4. KPI's | General | KPI's to be sent to Phil McMullan. | KPI's to be sent to Phil McMullan. | PM/PB | 22.8.16 | Closed
21.6.16 | .5. CONTRACTUAL |  |  | No issues to report |  | 21.6.16 | Closed
21.6.16 | .6. ENERGY | General | Energy / carbon reduction incentive | Kier new vans are energy efficient are also fitted with tracking devices. | Greg Jones | Closed | Closed
21.6.16 | .7. CAPITAL WORKS | Required sites | All pre-measures now received | John Bolton advised all pre-measures had now been received - John to attend arranged pre-start meeting. | JB | Closed | Closed
21.6.16 | .8. SITE CHANGES | Site | Tisbury Library | Re-opening at the new Tisbury Nadder Campus | PM | 14.9.16 | Closed
21.6.16 | .8. SITE CHANGES | Site | Calne Leisure Centre (White Horse Sports Centre) | WC responsibility effective form the 21/06/2016 | Phil | Closed | Closed
21.6.16 | .9. COMPLAINTS | General | Non received | No action required |  | 21.6.16 | Closed
21.6.16 | 10. COMPLIMENTS |  | Nothing to report |  |  | 21.6.16 | Closed
21.6.16 | .6. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard to advise if this is to fall under the remit of the Energy Team to Kier | PM/IG | Closed | Closed
26.7.16 | .1. REACTIVE | General | Order / Work Process | It was highlighted during the meeting that work orders were not being closed down and a new one raise in the event of parts ordering and extended time lines. Also there was not a consistency of procedures across the board. . Greg has provide a process flow chart for discussion Pm to hold a meeting next week to discuss and agree in the interim period prior to concerto. | PM / KB/ GJ | 14.9.16 | Closed
26.7.16 | .1. REACTIVE | Lime Kiln | Pre-measure | Discussions were held with regards to a Pre-measure carried out on at wall at Lime Kiln. This highlighted issues as detailed within the process and lack of resources | Note | Closed | Closed
26.7.16 | .3. EARLY WARNING | General | Early warnings | Non Issued |  |  | Closed
26.7.16 | .4. KPI's | General | KPIs | KPIs show a poor performance, however this is not a true reflection as it was identified that the order process being currently carried out has a major impact on results and also due to the fact that the results were not sense checked for exceptions Kier has also advised that kiers cafm system has had a mobile app upgraded which has effected the system hence kpis report has been affected | PB / PM | 25.10.2016 | Closed
26.7.16 | .5. CONTRACTUAL | General | Trowbridge offices | It was acknowledged that there has been various difficulties in providing an expected service level through resources / location / technology at this stage of the contract. Kier has now taken processes of local premises and appointed permanent local employees to manage the contract. This will have a profound noticeable impact once training has been completed (October) and with the long awaited anticipated software, processes should have a more auditable working platform | All | 25.10.2016 | Closed
26.7.16 | .6. ENERGY | General | Energy / carbon reduction incentive | Non reported | all | Closed | Closed
26.7.16 | .7. CAPITAL WORKS | General | Capital Works process | LG to seek and distribute a formal process of notification for capital works | LG | 23.10.16 | Closed
26.7.16 | .7. CAPITAL WORKS | General | Capital works general | TS to provide list of capital works awarded CMA project only) | TS | 23.10.16 | Closed
26.7.16 | .7. CAPITAL WORKS | General | Capital works general | A system needs to be identified in the interim to concerto to highlight warranty works | LG | 23.10.16 | Closed
26.7.16 | .9. COMPLAINTS | General | Non received | No action required |  | 26.7.16 | Closed
26.7.16 | 10. COMPLIMENTS |  | Nothing to report |  |  | 26.7.16 | Closed
26..7.16 | .6. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard has confirmed that the DEC will be completed in house | IG/PM | Closed | Closed
|  | Toolbox Training | DBS for all staff | Paul Bramhall advise 1 staff member to be finalised on DBS | PB / PM | 22.8.16 | Closed
23.8.16 | .0. H&S | Toolbox Training | Toolbox training for all staff | Paul Bramhall advise 1 staff member to be finalised on DBS. Discussion held with regards to the importance of Sun protection working out side - Greg to forward list of item to be cover to Phil | PB / PM | Closed | Closed
23.8.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | UPDATE. Pete Wort/Dave Collier to supply report | PW | 14.09.2016 | Closed
23.8.16 | .2. SUBMISSION | General | Monthly Submission and cross service sectors | PB identified that there were still issues whereby works were being allocated to the incorrect lots on the order from the helpdesk. | PM | 14.9.16 | Closed
23.8.16 | .4. KPI's | General | KPIs | Greg advised a staff member will be employed to run KPI reports. Greg and Phil to discuss KPI processes in a separate meeting. | Phil/Greg | 25.10.16 | Closed
23.8.16 | .1. REACTIVE | Schools Site | School works exceeding threshold | Phil to arrange a separate meeting with Kevin to clarify orders over the value to £500.00and if need to be approved by the school. (Linked to item 65) | Phil | 25.10.16. | Closed
23.8.16 | .5. CONTRACTUAL | Trowbridge offices | Update on new offices from Greg there have been phone issues between Vodafone and Bt but this is hoping to be resolved by 01/09/2016. Also a further 2 full time members of staff have been employed. It has also been suggested live training between the kier helpdesk and WC helpdesk. Time and dates to be advised once Phil has spoken to Pip. | Update on new offices from Greg there have been phone issues between Vodafone and BT, this is hoping to be resolved by 01/09/2016. Also a further 2 full time members of staff have been employed. It has also been suggested live training between the kier helpdesk and WC helpdesk. Time and dates to be advised once Phil has spoken to Pip. | Phil | 14.9.16 | Closed
23.8.16 | .7. CAPITAL WORKS | General | Capital works general | Capital Works Projects to be returned to requesting Project Officer/Technical Officer to place further GVAs orders if required, | Phil | 23.8.16 | Closed
23.8.16 | .1. REACTIVE | Melksham Cemetery | Wall Works. | Tom advised the wall works at Melksham Cemetery has been stopped with no reason given by Kez Hutchens. Theo (procurement) advise Phil to speak to Ian Brown for further information. | Phil | 14.9.16 | Closed
14.9.16 | .0. H&S | Lower Lodge Farm | Lower lodge Farm - Heras Fencing was required around building. Contractor reported the building was unsafe. | UPDATE. Pete Wort advised cost estimates has been sent FAO Jenny Rowe - UPDATE further GVAs order place works completed | PW/Jenny Rowe | 22.11.16 | Closed
14.9.16 | .1. REACTIVE | Melksham Cemetery | Wall Works. | Kez advised the wall works at Melksham Cemetery has been stopped due to the increase in costs, which may requires the works to go out to tender. Kez has requested Kier to invoice and to send any documentation for her attention. | Pete Wort/ Kez | 23.10.2016 | Closed
14.9.16 | .8. SITE CHANGES | Site | Tisbury Library | To be confirmed with Darren Maplesden if this is now a void property and advise if services need to be drained down/capped off. | MW | 23.10.16 | Closed
14.9.16 | .1. REACTIVE | General | Order / Work Process | Update - It was highlighted during the meeting that work orders were not being closed down and a new ones raised in the event of parts ordering and extended time lines. Phil requested a daily report to be sent highlighting new orders to be raised. Report to be sent to HardFMcontracts team, Mo and Liza to then allocate to relevant persons to raise new orders. Kez also requested that any returned notifications sent to FM Support, that the relevant Technical Officer are CC'd into the e-mail. Peter to check with Kier staff if this is possible. | Pete/ Phil | 23.10.16 | Closed
14.9.16 | .1. REACTIVE | General | Priorities on GVAs orders | Pete advised that orders placed for 2hr & 24hrs had drop however he believed that certain orders should have been a 5 day plus . Phil asked for examples to be forwarded. | Pete/Phil | 23.10.16 | Closed
14.9.16 | .2. SUBMISSION | General | Monthly Submission and cross service sectors | PB identified that there were still issues whereby works were being allocated to the incorrect lots on the order from the helpdesk. Phil requested that the GVAs orders are sent to him so the issues could be addressed. | PW/Phil | Closed | Closed
14.9.16 | .4. KPI's | General | KPIs | Phil has advised the spreadsheet sent by Paul Bramhall and populated by Kier staff is unacceptable it does not provide sufficient information eg start and end date. Phil to liaise with Paul. | Paul/Phil | Closed | Closed
14.9.16 | .5. CONTRACTUAL | Trowbridge offices | The Kier offices are now up and running. It has been suggested live training between the Kier helpdesk and WC helpdesk, with WC staff visiting the Kier office and via a versa. Time and dates to be advised once Phil has liaised with Pip/Kez/Mark | The Kier offices are now up and running. It has been suggested live training between the Kier helpdesk and WC helpdesk with WC staff visiting the Kier office and via a versa. Time and dates to be advised once Phil has liaised with Pip/Kez/Mark UPDATE Phil advised due to changes within FM, this has now been postponed and will be reviewed at a later date. | Phil | 31.01.17 | Closed
14.9.16 | .5. CONTRACTUAL | QFM | The issues was raised gaining information from QFM has been difficult. | The issues was raised gaining information from QFM had been difficult. Tom advised there had been IT issues, but these have now been resolved, | All | 14.9.16 | Closed
14.9.16 | .1. REACTIVE | Corsham Campus works | Kez to set up a separate meeting with Kier to discuss. | Kez to set up a separate meeting with Kier to discuss. | Kier/Kez | 23.10.16 | Closed
14.9.16 | .1. REACTIVE | St Katharine's, Marlborough | OOH call placed following trees falling. | Kez advised there are still ongoing issue regarding responsibility for the damage caused by the trees and if the trees can be removed as it has a protection order against it. Kim Mounty is assisting the school with their insurance claim and liaising with the relevant parties involved. | Kim | 23.10.16 | Closed
14.9.16 | .1. REACTIVE | Bewley House, Chippenham | Bewley House Ground floor partition and decorating works. | Bewley House Ground floor partition and decorating works. Kez is leading on this project and will arrange separate pre-start meeting if required. | Kier/Kez | 23.10.16 | Closed
14.9.16 | .1. REACTIVE | Rowdeford School, Devizes | Rowdeford School, Devizes, Dome works. On-Going programme works | Rowdeford School, Devizes, Dome works. Pete advised the dome is starting to sink, supporting scaffolding is being erected and the area has been cordoned off. The dome had lead covering and make have to recovered like for like. Due to location the Conservation Team have now become involved and as yet no further works have been carried out. UPDATE Pete advised internal works are now being considered - Dave Gibson is now managing the Project further info to be forwarded to John Bolton Still ongoing John Bolton is now liaising with WC Structural Engineer on how to proceed. UPDATE Dave Gibson and Iwan Van Den Berg now leading on this project. Dave Gibson to confirm completion date to Iwan. UPDATE: Dave Collier now managing project - liaise with Iwan Van Den Berg. Est completion 30/05/17 UPDATE works have now been completed and invoiced | DC | 30.05.17 | Closed
14.9.16 | .2. SUBMISSION | Schools Site | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Kier | 19.1.16 | Closed
14.9.16 | .0. H&S | General | Staff monthly Tool Box talks | Greg to forward list of item to be cover to Phil | Greg/Phil | 25.10.216 | Closed
14.9.16 | 0.10. COMPLIMENTS | New Close School | New Close School toilet refurbishment. Kier received compliment from site stating Kier staff were efficient, clean and polite while on site carry out the works | New Close School toilet refurbishment. Kier received compliment from site stating Kier staff were efficient, clean and polite while on site carry out the works | Phil | 14.9.16 | Closed
25.10.16 | .8. SITE CHANGES | Site | C4 & C5 Hopton Devizes | This site is now closed when services is required keys to be collected from County Hall FM Office. Mike Dawson is the lead on info for this site. | Mike Dawson | 20.12.16 | Closed
25.10.16 | .8. SITE CHANGES | Site | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodmans is leading on this project | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodman is leading on this project. All services put on hold until further notice. | Tim Goodman | 28.02.2017 | Closed
25.10.16 | .1. REACTIVE | St Stephen Car Park | Entrance works | Adam requested update on the works to the entrance bull bars . Tom advised Pete was working on the fabricating of the bull bars. Paul B to speak to Pete for an update. Update works to be completed 23/11/2016 | Paul/Pete/John Bolton | 22.11.16 | Closed
25.10.16 | .4. KPI's | General | KPIs | Phil to hold a separate meeting with Kier to discuss | Phil | Closed | Closed
25.10.16 | .5. CONTRACTUAL | General | Uplift on MTC threshold. | To be discussed if threshold to be raised from £50.000.00 - amount to be agreed with Procurement. Phil to liaise with Kevin - UPDATE Phil has advised he has spoken to Procurement and was just waiting for a confirmation letter. Phil also advised he will be releasing several FMC works to Kier above the £50.000 threshold. Kevin has documentation which requires Barry Pirie's approval. Phil to keep Kier updated. UPDATE The process has now been agreed and now only waiting for WC's legal department to send acceptance letter out to Kier for signing.. UPDATE: PM to chase legal/TB for official letter to Kier. | Phil/Kevin | 30.05.2017 | On-going
25.10.16 | .7. CAPITAL WORKS | General | Capital works general | Liza advised completed list has now been sent to Education for approval. Kier advised Education have cut the budget which will impact on works to be carried out. Greg requested approved list to be forwarded when works are known. Phil to peak to KB on sending on relevant information UPDATE Kevin has been to several meetings in which he has raised the issue of the Corporate Risk. FMC works still not being released as still require approval. Contractor advised to still check the South West Portal. Update: FMC 16/17 all orders raised and issued. DC to email Iwan to confirm any 16/17 outstanding works. CMA 17/18 Projects list sent to Kier (Indicative). Scope of works to be clarified and priced. Site meetings being held with WR for clarification.UPDATE Site visits have now been completed and costed, with order now being placed. FMC works now have to be approved via the 'gateway. excepted approval dates middle of June. | Phil | Open | On-going
25.10.16 | .8. SITE CHANGES | Site | Little Folly Children Centre (Winding Way) UPRN 01153S2 | Closed - nursery (South hill School) are taking on the whole of the building GVAs ORDER 106689 TO BE RE-INSTATED | Anna Cox | 20.12.16 | Closed
25.10.16 | 0.10. COMPLIMENTS | Durrington Infants & Larkhill School | Durrington Infants & Larkhill School complimented Kier on there workmanship . | Durrington Infants & Larkhill School complimented Kier on their workmanship . | Pete/Tom | 25.10.16 | Closed
25.10.16 | .9. COMPLAINTS | General | Non received | No action required |  | Closed | Closed
25.10.16 | .1. REACTIVE | General | Z1 reports. | Phil to arrange a separate meeting with Greg to discuss re-occurring issues | Phil/Greg | 22.11.16 | Closed
25.10.16 | .2. SUBMISSION | Schools Site | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Kier | 22.11.16 | Closed
25.10.16 | .2. SUBMISSION | General | Monthly submission | No issues reported | PM | 25.10.16 | Closed
25.10.16 | .4. KPI's | General | KPI performance | PB to forward KPI reporting not sense checked due to IT issues | PB | 05.11.16 | Closed
25.10.16 | .8. SITE CHANGES | Tisbury | Closure | Tisbury Library now closed |  | Closed | Closed
22.11.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul advised only 1 member of staff still requires DBS clearance. | Paul Bramhall | 20.12.16 | Closed
22.11.16 | .1. REACTIVE | Kingsbury Square & PSL site | Property clearance | Pete W requested clarification if grass cutting - removal of fridges, cleaning carpets of theses properties should fall under the remit of Kier as he believe this was not part of the contract. Phil to liaise with Kevin. Phil has requested a breakdown of prices which he can then present to Kevin. UPDATE Pete still to supply cost for Phil. Greg advised works of the above would be undertaken by sub-contractor. Also advised the removal of electrical goods would be at an extra cost due to disposal. | Phil/Pete | 31.01.17 | Closed
22.11.16 | .2. SUBMISSION | General | Submission time scales | Paul advised staff have been allocated to clear back log of O/S work orders. Kier again advised to prioritise schools as they are chasing when they will be invoiced. Figure received show that there are still 600 fabric works orders to be invoiced. Phil to arrange separate meeting to discuss these ongoing issues. - Greg advised staff were still working to clear backlog. Phil to arrange separate meeting in January on how to clear backlog of outstanding invoices for Schools Greg advised there was now 450 fabric works still o/s. Greg advised staff have been allocated to clear back log of O/S work orders. Following a request from Phil to produce accrual costs for school this has now been blocked as cost could be incorrect, to receive accurate costs each job would have to be measured. As the school are chasing o/s invoices Phil to formally write to Kier requesting a completion date. Phil to also discussed the issue with the o/s invoices for schools with Kevin. UPDATE backlog of invoices still ongoing with Schools having priority. Phil advised he had raised an early warning notice and expected the backlog to be cleared during March, UPDATE:Kier are submitting applications on a regular basis to catch up. PM stressed all reactive works up to Dec must be invoiced. Kier advised 12 week turn around. PM stressed concern about aged debt exceeding 3 months. UPDATE Greg advised as Kier's end year is June he wanted as many submission completed and invoiced asap. Vincent advised expected date of closure of GVAs end of June.any outstanding orders to then be transferred to Concerto | Paul Bramhall | 30.04.17 | On-going
22.11.16 | .3. EARLY WARNING | General |  | Non Issued |  | 22.11.16 | Closed
22.11.16 | .4. KPI's | General | KPI performance | Phil to hold a separate meeting with Kier to discuss. UPDATE Phil to hold separate meeting with Paul Bramhall in January 2017 | Phil | 31.01.17 | Closed
22.11.16 | .5. CONTRACTUAL | Kingsbury Square & PSL site | Grass cutting, rubbish removal, carpet cleaning | Pete W requested clarification if grass cutting - removal of fridges, cleaning carpets of these properties should fall under the remit of Kier as he believe this was not part of the contract. Phil to liaise with Kevin. Phil as requested breakdown prices which he present to Kevin. | Phil/ Pete | 22.11.16 | Closed
22.11.16 | .6. ENERGY | General | Nothing to report | Nothing to report |  | Closed | Closed
22.11.16 | .7. CAPITAL WORKS | General | Capital works general | Phil advise some pre-measure works have now been release site included Amesbury Leisure Gym works (Andrea waiting for costs). Olympiad Leisure, tank works, lift and soffit works. Bradford on Avon chemical stores. UPDATE Phil to keep Kier updated with further meeting to be arrange in January 2017 UPDATE Phil advised approval had now been received for additional works to be carried out with orders being raised by the end of March. . UPDATE: Westbury Pool Door to be completed 28.03.17. | Phil | 30.05.2017 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01400S1 | Bowerhill Melksham PDC Lancaster Road SN12 6SP | Site has now been sold can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01067S3 | Corsham Regis Children Centre SN13 0EG | CLOSED - nursery (South Hills) are taking over whole building can be removed from PPM Planner GVAs ORDER 106588 TO BE RE-INSTATED |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01121S2 | Malmesbury Children centre SN16 9JR | CLOSED - premises will be handed back to school can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 40035S1 | Corner House Children's Centre George Lane CP Marlborough SN8 4BY | Site is closed can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01610S2 | Five Wishes Children's Kitchener Road Amesbury SP4 7AA Centre | CLOSED - nursery (Smiley Faces) are taking over whole building. Can be removed from PPM Planner GVAs ORDER 106679 TO BE RE-INSTATED |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01655S1 | Wilton Children's Centre ( West Street Wilton SP2 0DL | CLOSED - vacant - notice has been served to terminate the lease. Can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01557S1 | Ludgershall YC, Andover. SP11 9LZ | This site is now void and all services have been isolated and drained down , all works to be put on hold as advised by John Price. Keys held in the FM key cabinet, hook 72 BH |  | 31.01.17 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 30007S2 | The Barn Penny farthing - Salisbury SP1 | Remove from PPM planner as this site is part of PF House which has now been sold. QFM 149584 (No GVAs order has been placed) |  | 20.12.16 | Closed
22.11.16 | .8. SITE CHANGES | UPRN 01008S1 | The John Ivie Centre (Exeter House) | Remove from PPM planner, WC have no responsibilities for this site as advised by John Price/Mark Murnane QFM 150197 (No GVAs order has been placed) |  | 20.12.16 | Closed
22.11.16 | .0. H&S | Riddor - Reporting of Injuries | 2 incidents to report | 1) Reported a engineer receiving a dog bite at a gypsy site. 2) Engineer received a finger injury while handling a drill |  | 20.12.16 | Closed
22.11.16 | .9. COMPLAINTS | Amesbury Primary School. | Reported to Andrea Baker | Attendance had been arrange during school holidays, engineer went sick, but the school was not informed. Pete confirmed that procedures were in place but had not been followed, this has now been resolved and new appointment made with the school. | Andrea | 22.11.16 | Closed
22.11.16 | 10. COMPLIMENTS |  | Nothing to report |  |  | 22.11.16 | Closed
22.11.16 | .1. REACTIVE | School sites | Gym equipment | Andrea advised that several schools, one being Wilton & Barford have shown at interest in having their gym equipment fall under the remit of WC/Kier. Andrea has been liaising with Dave Gibson who is on the process of supplying costs. Pete to also source contractor capable of carry out required works, Phil to arrange a separate meeting in January 2017 to discuss further, what would this involve, if works would be given to sub-contractors. etc etc. UPDATE Dave Gibson still to supply required information | Dave Gibson | 22.11.16 | Closed
20.12.16 | .0. H&S | Bourne Hill Salisbury | Aria Engineer having to gain access to plant room through roof hatch. | Mark advised the Aria engineer had difficulties gain access through the roof hatch to the top plant room. Mark to liaise with Corporate Health, on how to proceed. Greg also advised a Risk Assessment is required to be carried out by all attending engineers on safety when entering confined spaces. | Mark | 20.12.16 | Closed
20.12.16 | .2. SUBMISSION | General | Fabric works from application not being paid | Several payment have been held back from being paid by the Technical Officers. Greg has advised this has an impact on Kier's cash flow as the works have been completed. Phil to look into new process, if Tech Officers are still holding back on full payment that Kier could receive possible interim payments . UPDATE Melksham Cemetery payment still being with held by Kez who is liaising with procurement. UPDATE: PM advised that this has not been resubmitted. UPDATE Greg to advise if all payments have now been received. | Phil/Kez | Open | On-going
20.12.16 | .3. EARLY WARNING | General |  | Non Issued |  | 20.12.16 | Closed
20.12.16 | .5. CONTRACTUAL | General | Sub-contractors proof of management | Phil has requested proof of how Kier manage/check their sub-contractors,. Greg advised there is a process in place that all sub-contractors are checked. Greg to forward to Phil relevant documentation on processes UPDATE Phil still waiting for relevant doc's . Greg to forward to Phil as requested. | Greg/Phil | 30.05.2017 | Closed
20.12.16 | .5. CONTRACTUAL | General | Sub-contractors - Ringing managers direct. | It was reported by Kevin B that he had been receiving calls direct from Sub-contractors (TH White). Tom advised he will speak to Sub-contactor as they were aware of the process. | Tom | 20.12.16 | Closed
20.12.16 | .6. ENERGY | General | Nothing to report | Nothing to report |  | 20.12.16 | Closed
20.12.16 | .9. COMPLAINTS | Devizes Resource Centre | OOH issue | An issues had been reported on an incident following an OOH call. Tom advised incorrect information had been passed to the sub-contractor. Greg will be holding a separate meeting in January 2017 with the OOH call centre operatives to discuss how this issues will be resolved. | Phil/ Greg | 20.12.16 | Closed
20.12.16 | .9. COMPLAINTS | Various | Great Bedwyn re-leak. Issue with sub-contractor TWC. Sub-contractors arriving on site without DBS documentation. | All issues have now resolved | Phil | 20.12.16 | Closed
20.12.16 | .9. COMPLAINTS | Melksham Cemetery | Regarding the fencing at Melksham Cemetery | Works had been put on hold from Kez on the instructions of Procurement. Phil has requested documentation on scope of works sent to Kier. Phil to also liaise with Procurement for an update on what is happening at the site. Kez has still with held payment for works already completed by Kier. Phil to investigate UPDATE approx £30000.00 has now been released for payment by Kez. | Phil | Closed | Closed
20.12.16 | 10. COMPLIMENTS | Bourne Hill Salisbury | Mark complimented both Chris Bradshaw and Dave Gibson on their high standard of work and their professionalism | Mark complimented both Chris Bradshaw and Dave Gibson on their high standard of work and their professionalism. Paul to pass comments on to the individuals | Paul Bramhall | 20.12.16 | Closed
20.12.16 | .1. REACTIVE | Salisbury Library | Engineer had attended Site (Les) closed works before the job had been completed | Mark advised works had not been completed but the job had been closed, it was not until he attended site he was informed the works were still ongoing. Mark spoke to Dave Gibson who arranged for the works to be completed. | Mark | 20.12.16 | Closed
20.12.16 | .1. REACTIVE | Bradbury House, Salisbury | Lamp works still not completed | Mark advised the lamp post works had still not been completed, Mark to forward documentation to Pete regarding these works as they have been ongoing since the start of the new contact. UPDATE Tom advised the works are commencing on the 09/03/2017. TS advised works complete | Mark/Pete | 31.01.17 | Closed
20.12.16 | .1. REACTIVE | General | Volume of fabric orders being placed to Kier | Greg advised due to the drop in the amount of fabric orders being received from WC he may need to reduce his work force accordingly. | Greg | 20.12.16 | Closed
31.01.17 | .0. H&S | Riddor - Reporting of Injuries | 1 incidents to report | Reported a engineer receiving a dog bite at a gypsy site. Pete to send details to Phil who will escalate information to Mike Davis | Phil/Pete | 31.01.17 | Closed
31.01.17 | .0. H&S | General | Engineers not signing asbestos register. | Pip advised when engineers attend County Hall when signing for their visitors badges, they will be required to tick a box confirming they has seen the asbestos register. | Pip | 31.01.17 | Closed
31.01.17 | .0. H&S | General | DBS identification | An issue was raised when engineers attended a school site when asked to produce their DBS cert the site was told they did not carry one. Greg advised all Kier engineers carry ID. Sub-contractors need only supply their ID no's - photos not required as per contract. Phil to check contract and advise accordingly. UPDATE Paul now advised that sub-contractors have all been a told to carry identification with them when visiting WC sites. | Phil | 31.01.17 | Closed
31.01.17 | .1. REACTIVE | General | Additional works | Pip advised when engineers attend County Hall to carry out reactive works the engineer was asked if he was also on site to carry out another job. The engineer explained he had only received one job. As the jobs has been input a day apart he would have to re-attend. Greg advise FM to liaise with Kier Helpdesk and advise engineer works can be carried out saving both time and money for both parties involved. | Pip | 31.01.17 | Closed
31.01.17 | .3. EARLY WARNING | General |  | Non Issued |  | 31.01.17 | Closed
31.01.17 | .4. KPI's | General | KPI performance | Phil to keep monitoring KPI performance due to Kier now reducing resources, which could have impact on KPI figures - UPDATE Phil advised there had been an improvement with figures. Phil to arrange a separate meeting to discuss Budget Estimate and Pre-measure and 10 day + as these are having an impact on the KPI figures. | Phil | 31.01.17 | Open
28.02.17 | .0. H&S | Calne Leisure Centre | Asbestos tile debris left on site by Encompassed | Pete advised Asbestos tile debris had been left on site by Encompassed Sub-Contractors (Ring). Relevant report to be raised and sent to Iwan and Kim. | Pete | 28.02.17 | Closed
28.02.17 | .1. REACTIVE | County Hall Trowbridge | County Hall cracked window at the front of the building | Tom advised that Kier Construction and Corsham Building Plastics, who installed the window have no details regarding the original window fitted. Tom has now been advised by Phil, to confirm this in writing to Pip and Kevin and suggest a way forward to resolve the issue with an option to supply new samples. UPDATE: TS confirmed that PW advised has been passed to Kier Central Procurement to look into | Tom | 28.03.17 | Open
28.02.17 | .1. REACTIVE | Chippenham Olympiad Leisure Centre | Pre-measure works to the fascias and soffits and windows around the building | Paul Calloway had attended site to raise Pre-measure for the replacement of the fascias and soffits around the whole of the building. When pre-measure produced it was for the front of the building only, when this was raised with Paul he confirmed that he had not checked the back of the building. Paul Bramall to liaise with Paul Calloway and update Phil with correct figures. UPDATE: DC advised order raised and VO issued. Start 31/03/17 - completion within 8 weeks. UPDATE Tom advised 1st phase of works have been completed and remaining to be completed by the end of June | Paul/hil | 30.05.17 | Open
28.02.17 | .3. EARLY WARNING | General | No action taken | Non Issued |  |  | Closed
28.02.17 | .6. ENERGY | General | Nothing to report | Nothing to report |  | 20.12.16 | Closed
28.02.17 | .8. SITE CHANGES | UPRN 01506S1 | DevizesYDS OP HQ | DevizesYDS OP HQ 01506S1 Remove from PPM Schedule as site has been handed back to landlord no longer under WC remit | Open | Open | Open
28.02.17 | .8. SITE CHANGES | UPRN 40001S6 | Devizes Yew Trees | Devizes Yew Trees 40001S6 Remove from PPM Schedule as site no longer under WC remit (Julia’s House have full responsibility) | Open | Open | Open
28.02.17 | .8. SITE CHANGES | UPRN 30007S1 | Penny Farthing House | Sold | SOLD - 01/07/2016 | Open | Open
28.03.17 | .0. H&S | General | Confined Spaces | Kier requested list of confined spaces. PM advised that WC do not have a list and Kier need to compile a list from engineers. TS to arrange meeting to compile with PM | Tom/Phil | 28.04.17 | Closed
28.03.17 | .0. H&S | General | Staff monthly Tool Box talks | Continues with Engineers who receive handouts and give feedback to highlight issues | Kier | 28.04.17 | Closed
28.03.17 | .2. SUBMISSION | General | Schools | PM advised until schools have confidence that the delay in invoicing has been resolved they are holding back works | PM | Closed | Closed
29.03.17 | .3. EARLY WARNING | General | Early warnings | Kier issued No 4 re: Audit Process. PM established there is a process and will adapt it to fit | Phil | Open | Open
29.03.17 | .5. CONTRACTUAL | General | Sub Contractors | PM still waiting for documents. TS to provide in GJ absence | Tom | 30.04.17 | Closed
29.03.17 | .5. CONTRACTUAL | General | Organisational Structure | PB provided organisational chart but PM requested official notification of Senior Change in Management. Still waiting | PB | 30.04.17 | Closed
29.03.17 | .5. CONTRACTUAL | General | Social Values | Noted that Kier did undertake a project at Cotswold House | N/A | N/A | Closed
29.04.17 | .8. SITE CHANGES | UPRN 01697S1 | The Big Shed Folly Road Devizes | Handed back to the Landlord on the 29/04/2017. This property in avoid Permanent Void – building empty and not to be re-occupied | Open | 29.04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPR N 01406S1 | Warminster Youth Development Centre, The Wave, The Close, Warminster BA12 9AL | Now under the remit of the Parochial Church Council of Christ Church Youth Club. No longer WC Responsibility | Open | 01 .04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 40010S1 | Devizes Couch Lane, 7 Couch Lane, Devizes SN10 1EB | Lease Out to Guy’s Magnets Ltd | Open | 31.03.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 30057S1 | Salisbury Fisherton Clock Tower | SOLD to Salisbury City Council | Open | 01.04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 30022S2 | Salisbury Culver Street PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Open | 01.04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 30026S2 | Salisbury Millstream Approach Coach Station PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .8. SITE CHANGES | (UPRN 30017S2) | Shopmobility, The Maltings, Salisbury SP2 7TL | Shopmobility, The Maltings, Salisbury SP2 7TL has now been transferred to Salisbury City Council with effect from 1st April 2017? | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 10044S2 | Chippenham Bath Road Public Conveniences | Now under the remit of Chippenham Town Council 20/04/2017 | Handed over to Chippenham Town council from the 20/04/2017 | 20.04.2017 | Open
29.04.17 | .8. SITE CHANGES | UPRN 01697S1 | Devizes Folly Road Warehouse (Big shed) | Lease has now been terminated 29/04/2017 | Lease has now been terminated 29/04/2017 | 29.04.2017 | Open
30.05.2017 | .1. REACTIVE | County Hall Trowbridge | County Hall re-tiling of plinth structure o/s of C/H | Vincent requested works to be completed by the 19th June. Tom advised due to the issue of matching the tiles Kier may not be able to complete works in the allocated time frame. Greg suggested a form of advertising boarding. Vincent to liaise with Barry Pirie | Vincent/ Tom | 19.06.17 | Open
30.05.2017 | .1. REACTIVE | County Hall Trowbridge | Council Chambers window covering | Dave Collier to supply options (Blinds - Tints) and budget figures re the window in the Council Chambers, | Dave Collier/ Phil | 30.05.17 | Open
30.05.2017 | .1. REACTIVE | General | General | Kier to produce a WIP (works in progress) and a JIP (Jobs in progress) reports. This is to be an interim process until Kier new system Concept is completed and live by the end of September. Phil and members of Kier will have weekly meetings (Tuesdays) to discuss any outstanding issues. Vincent showed Kier the Suppliers Portal on Concerto were job status information can exported to by Kier. | Kier/Phil | 30.05.17 | Open
30.05.2017 | .1. REACTIVE | General | Blue 9 and Kier OOH Service | Phil advised several issue had been raised that when Blue 9 call Kier OOH that no reference no is given and some call are taking up to an hour to be answered. Greg advised once a call is received a reference no is automatically produced. Greg to request reports from the OOH support line which will shoe required details. Phil advised Kier to liaise with Sarah Peters as the Blue 9 contract fall under her remit. | Kier/Phil | 30.05.17 | Open

## M&E (hidden)
. | LOT 2 | MECHANICAL & ELECTRICAL | MONTHLY MAINTENANCE CONTRACT MEETINGS
| DATE | 2017-05-30
| ATTENDEES | Phil McMullan (WC) Maureen Wells (WC) Tom Somerville (Kier) Pete Wort (Kier) Greg Jones (Kier) Vincent Albano (WC)
| APOLOGIES | Paul Bramhall (Kier) Liza Gordon(WC)
| MT | Maureen Wells
DATE Example 26.4.16 | AGENDA CATEGORY | SITE / LOCATION / GENERAL | BRIEF DESCRIPTION | COMMENTS | PERSON TO ACTION | DATE TO BE ACTIONED BY | STATUS
.0. H&S
.1. PPM
.2. REACTIVE
.3. SUBMISSIONS
.4. EARLY WARNINGS
.5. KPIs
.6. CONTRACTUAL
.7. ENERGY
.8. CAPITAL WORKS
.9. SITE CHANGES
10. COMPLAINTS
11. COMPLIMENTS
26.4.16 | .0. H&S | General | No issues raised | No Action Required |  |  | Closed
24.5.16 | .1. PPM | Sites as required | Statutory servicing only to have priority this month. | Kier to monitor from planner | Tom Somerville | 24.5.16 | Closed
26.4.16 | .1. PPM | All sites | PPM Planner for all sites | To be sent to Phil McMullan W/E 29/04/2016 | Greg Jones | 29.4.16 | Closed
26.4.16 | .2. REACTIVE | All sites | Asset list to be revised | Spread sheet / data base to be set up | Phil Mc/Mo | 26.5.16 | Closed
26.4.16 | .2. REACTIVE | All sites | Any order to the value of £300.00 GVAs order to be requested via WC Helpdesk. Above this value to be sent to Technical office for approval. | Any issues to be forwarded to Technical Officers | Phil Mc | 21.6.16 | Closed
26.4.16 | .2. REACTIVE | Schools Site | School works exceeding threshold | Decision to be made on site if possibility of school closing, engineer to ring either WC helpdesk or Technical Office of the issues on site. Any other issues any order over the value to £500.00 to be approved by the school. | Tom Somerville | 24.5.16 | Closed
26.4.16 | .6. CONTRACTUAL | General | Greg Jones to supply costing of hourly rate of Control Engineer | Permanent or as required costing | Greg Jones |  | Closed
26.4.16 | .6. CONTRACTUAL | General | Wallgate/ Green flush costings (Tom to make further enquires) | Iwan Van Der Berg suggested wallgate unit may be under remit of Churchill's. Kier to discuss with PM regards site that have the units . Kier to manage | Tom Somerville | 24.5.16 | Closed
26.4.16 | .7. ENERGY | Sites with Biomass | Energy to decide if any issues with Biomass are reported via them in the first instance | WC Helpdesk to be advised of any changes | Ian Gillard/Jenny Watson | 24.5.16 | Closed
26.4.16 | .4. EARLY WARNINGS | General | Greg Jones raised early warning due to documentation impact not being loaded onto Concerto | Ian Gillard to lead on Concerto | Ian Gillard | 24.5.16 | Closed
26.4.16 | .5. KPIs | General | KPI's to be sent before next meeting so any issues can be raised. | To be sent to Phil Mc | Phil Mc |  | Closed
26.4.16 | .9. SITE CHANGES | All Site | Kier to be informed of any changes to site e.g.. voids, or no longer WC responsibility | Mo/Liza to advise | Mo/Liza | 21.6.16 | Closed
| .7. ENERGY | Olympiad Leisure Centre | Costing for wet side & general areas fore replacement LED lighting | Phil to liaise with Ian Gillard | Phil Mc | 24.5.16 | Closed
26.4.16 | .3. SUBMISSIONS | General | 3rd week of every month | Mo to process as required | Mo | 24.5.16 | Closed
26.4.16 | 11. COMPLIMENTS | General | Non reported | No Action required |  | 26.4.16 | Closed
26.4.16 | 10. COMPLAINTS | general | Non reported | No Action required |  | 26.4.16 | Closed
26.4.16 | .8. CAPITAL WORKS | General | Contractor advised to check South West Portal. If any works under £40.000 works will be awarded to contractor and order placed on GVA |  | Kier | 24.5.16 | Closed
24.5.16 | .0. H&S | General | No issues raised | No Action Required |  |  | Closed
24.5.16 | .1. PPM | All sites | PPM Planner for all sites | To be sent to Phil McMullan | Greg Jones | 01.6.16 | Closed
24.5.16 | .1. PPM | Sites as required | Statutory servicing only being carried out. | Statutory servicing only being carried out from previous contractors planners. Documentation to be added to QFM | Tom Somerville | 21.6.16 | Closed
24.5.16 | .1. PPM | All sites | New asset following site visits | To be added to planners and extra costings | Tom Somerville | 21.6.16 | Closed
24.5.16 | .2. REACTIVE | Schools Site | School works exceeding threshold | To clarify orders over the value to £500.00 to be approved by the school. Phil advised this to be added on to the agenda for the purposed open day on the 06/07/2016 for school that have re-joined the compliance scheme. | PM | 06.7.16 | Closed
24.5.16 | .3. SUBMISSIONS | General | 3rd week of every month | Mo to process PPM submission as required corresponding documentation located in QFM | Mo | 21.6.16 | Closed
24.5.16 | .2. REACTIVE | Leighton | Skip Hire | As this is for general waste, to be invoiced as agreed by Phil to be allocated against CH budget. | Phil Mc | 21.6.16 | Closed
24.5.16 | .4. EARLY WARNINGS | General | No action taken | No action taken |  |  | Closed
24.5.16 | .5. KPIs | General | KPI's to be sent to Phil McMullan to discuss process. | Phil and Paul to discuss in separate meeting | Phil/Paul | 21.6.16 | Closed
24.5.16 | .6. CONTRACTUAL | General | Wallgate/ Green flush costings (Tom to make further enquires) | Wallgate/ Green flush costings (Tom to make further enquires) | Tom Somerville | 23.9.16 | Closed
24.5.16 | .6. CONTRACTUAL | General | Greg Jones to supply costing of hourly rate of Control Engineer. TBC with Phil. | Greg Jones to supply costing of hourly rate. TBC with Phil in a separate meeting then again to be discussed at the contractors quarterly meeting. | Greg Jones | 21.6.16 | Closed
24.5.16 | .7. ENERGY | Trowbridge Sports Centre | Replacement LED lighting | Replacement LED lighting as agreed with Ian Gillard | Ian Gillard | 21.6.16 | Closed
24.5.16 | .7. ENERGY | Sites with Biomass | Energy to decide if any issues with Biomass are reported via them in the first instance | WC Helpdesk to be advised of any changes. Phil also to liaise with Ian. | Phil Mc | 21.6.16 | Closed
24.5.16 | .6. CONTRACTUAL | Olympiad Leisure Centre | Replacement LED lighting | to be carried out 13/14/15/ June 2016 | Tom Somerville | Closed | Closed
24.5.16 | .6. CONTRACTUAL | General | Works advised to be carried out after service visit. | Tom advised works required to be carried out after service visit are not being carried out following quotation which is open for 30 days. Tom to send weekly report to Phil with sites and recommendations to access. | Tom/Phil | 21.6.16 | Closed
24.5.16 | .8. CAPITAL WORKS | General | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA. FMC works to be submitted to Committee at the end of June. | Kier | 21.6.16 | Closed
24.5.16 | .9. SITE CHANGES | Site | Site changes | Pennyfarthing House, Salisbury - no longer WC property from the 01/07/2016.Kevin to liaise with developer if site to be decommissioned of all services. Calne Leisure Centre to be added to list from 21/06/2016 | Kevin/Phil | 21.6.16 | Closed
24.5.16 | 10. COMPLAINTS | general | Complaint regards an M&E Engineer working in Devizes | This issues has now been resolved with Kier's HR dept. | PB | 24.5.16 | Closed
24.5.16 | 11. COMPLIMENTS | General | Non reported | No Action required |  | 24.5.16 | Closed
21.6.16 | .0. H&S | Risk Assessments | Kier Staff | Toolbox training for staff on Slip, Trip, Falls. Dog Bites. Drink, Drugs. | Greg Jones | Closed | Closed
21.6.16 | .1. PPM | All sites | PPM Planner for all sites | PPM planner had been sent to Phil. Further discussion required. Phil to arrange a separate meeting. Greg advised as the PPM planner is a 'live document' this year it will be corrected with correct site assets. | Phi Mc | Closed | Closed
21.6.16 | .1. PPM | County Hall | County Hall works | John Bolton had concerns as Stuart Walker was no longer the resident engineer located at CH routine checks were being missed.. John also reported the AHU filters required changing 3 monthly not 6. Tom to liaise/meet with John to discuss. | John Bolton/Tom | Closed | Closed
21.6.16 | .1. PPM | Calne Leisure Centre | Calne Leisure Centre | Calne Leisure Centre now WC responsibility from the 21/06/2016. Phil, Pete, Tom to discus assets to be added to PPM. | Phil/Pete/Tom | Closed | Closed
21.6.16 | .2. REACTIVE | All Sites | All site | Clear definition of who will place orders from works referred back to the Helpdesk or when have to be referred to Technical Officers. Phil to advise | PM | Closed | Closed
21.6.16 | .2. REACTIVE | General | OOH phone calls | Greg Jones to advise how many calls Kier are receiving between 8.00 and 8.30 before the WC helpdesk opens. | GJ | Closed | Closed
21.6.16 | .2. REACTIVE | All sites | Out standing works | Phil had received several e-mail from Technical Officers, Delivery Managers for O/S works still not completed. Andria Baker reported Wilton Park & Ride works were over due by 6 weeks. New Close School Lighting overdue since March. Greg requested that all correspondence be sent to him so that that he could investigate further. Greg also requested any issues be sent to him prior to the contractors meeting so that he could advise accordingly. | PM / GJ | 25.10.16 | Closed
21.6.16 | .3. SUBMISSIONS | General | Data information required on PPM | Phil to discuss in separate meeting data required on the PPM submission. Phil & Greg to discuss costs, percentages cost for 'Specialists' Tom and Phil to agree Specialist List | Phil/Greg/Tom | Ongoing | Closed
21.6.16 | .4. EARLY WARNINGS | General | Phil McMullan raised early warning notice - on not receiving PPM Planner | Phil to liaise with Greg. | Phil/Greg | Ongoing | Closed
21.6.16 | .5. KPIs | General | KPI's to be sent to Phil McMullan | Phil and Paul to discuss in separate meeting so targets can be met. | Phil/Paul | 25.10.16 | Closed
21.6.16 | .6. CONTRACTUAL | General | Paul to send weekly report of any extra works required following service visits | Paul to send weekly follow up report of any extra Z1 status works required following service visits | Paul | 21.6.16 | Closed
21.6.16 | .6. CONTRACTUAL | Schools Site | Schools requesting costing | John Bolton advised Schools are requesting costs before further works are carried out following service visit. Issue to be raised at the 'Open Day' | Phil Mc | 06.7.16 | Closed
21.6.16 | .7. ENERGY | Sites with Biomass | No Heating | Any issues with heating and the site has Biomass order to be raised with Kier in the first instance. Should the fault be with Biomass plant, Energy to be contacted to organise attendance with specialist contractor | Phil Mc | 23.08.16 | Closed
21.6.16 | .8. CAPITAL WORKS | General | Contractor advised to check South West Portal. | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA. Kevin advised FMC works to be submitted to Committee for approval at the end of July. | Kier | Closed | Closed
21.6.16 | .9. SITE CHANGES | Site | Tisbury Library | Re-opening at the new Tisbury Nadder Campus | Phil | 14.9.16 | Closed
21.6.16 | .9. SITE CHANGES | Site | Calne Leisure Centre (White Horse Sports Centre) | WC responsibility effective form the 21/06/2016 | Phil | 23.9.16 | Closed
21.6.16 | 11. COMPLIMENTS | County Hall | County Air Conditioning issues | John Bolton complimented Kier for their performance with regards to the issues within CH and the non working air conditioning |  | 21.6.16 | Closed
21.6.16 | .1. PPM | County Hall | County Hall - HV contracted to SSE | Phil has agreed to place the HV contract with SSE under the Kier contract | Phil / Tom | 21.6.16 | Closed
21.6.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advised 3 member of staff still require DBS clearance. | P Bramhall | 23.9.16 | Closed
21.6.16 | .7. ENERGY | General | Energy / carbon reduction incentive | Kier new vans are energy efficient are also fitted with tracking devices. | Greg Jones | Closed | Closed
21.6.16 | .7. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard to advise if this is to fall under the remit of the Energy Team to Kier | Phil / Ian | Closed | Closed
26.7.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advise 3 staff member to be finalised on DBS | P Bramhall | 22.11.16 | Closed
26.7.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side | Staff meeting | Closed | Closed
26.7.16 | .2. REACTIVE | General | Order / Work Process | It was highlighted during the meeting that work orders were not being closed down and a new one raise in the event of parts ordering and extended time lines. Also there was not a consistency of procedures across the board. . Greg has provide a process flow chart for discussion Pm to hold a meeting next week to discuss and agree in the interim period prior to concerto. | PM / KB / GJ | 14.9.2016 | Closed
26.7.16 | .5. KPIs | General | KPIs | KPIs show a poor performance, however this is not a true reflection as it was identified that the order process being currently carried out has a major impact on results and also due to the fact that the results were not sense checked for exceptions | PB / PM | Closed | Closed
26.7.16 | .6. CONTRACTUAL | General | Trowbridge offices | It was acknowledged that there has been various difficulties in providing an expected service level through resources / location / technology at this stage of the contract. Kier has now taken processes of local premises and appointed permanent local employees to manage the contract. This will have a profound noticeable impact once training has been completed (October) and with the long awaited anticipated software, processes should have a more auditable working platform | All | 1.10.16 | Closed
26.7.16 | .7. ENERGY | General | Energy / carbon reduction incentive | Non reported | all | Closed | Closed
26.7.16 | .8. CAPITAL WORKS | General | Capital Works process | LG to seek and distribute a formal process of notification for capital works | LG | 23.6.16 | Closed
26.7.16 | .8. CAPITAL WORKS | General | Capital works general | A system needs to be identified in the interim to concerto to highlight warranty and update assets | LG | 23.7.16 | Closed
26.7.16 | .7. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard has confirmed that the DEC will be completed in house | IG/PM |  | Closed
26.7.16 | .1. PPM | All sites | PPM Planner for all sites | Pm still awaiting a full planner. TS to provide a copy this week however this will be a love document and amendments will be required as and when assets are identified. In particular Schools. | TS | 14.9.16 | Closed
26.7.16 | .1. PPM | General | Non compliance ppm | TS advised that Kier will now start to carry out PPM on Non Compliance service items. | TS | 23.9.16 | Closed
26.7.16 | .1. PPM | General | School assets and planner | PM and LG have now starting to produce a new school asset costing sheet which will also identify service dates for items not currently identified following in-house asset surveys. This will be completed during Sept 2016 | PM / LG / MC | 20.12.16 | Closed
26.7.16 | .3. SUBMISSIONS | General | Monthly Submission | PM rejected a submission due to non-approve up-lift cost being applied. Submission should be re-submitted as per contract. GJ highlighted that its confusing with regards to specialist and non specialist works and requested that the percentage could be changed. PM advised that it could be taken into consideration in the 18 month review. | PM | Closed | Closed
26.7.16 | .3. SUBMISSIONS | PPM | Monthly Submission | PB to forward a copy of the new format with regards to PPM submissions to PM | PB | 23.10.16 | Closed
26.7.16 | .4. EARLY WARNINGS | General | No action taken | No action required |  |  | Closed
26.7.16 | 10. COMPLAINTS | general | Non reported | No Action Required |  |  | Closed
21.6.16 | 11. COMPLIMENTS | Trowbridge Sports Centre | Pool Lighting | Compliments received from PFP Tech manager and Site the works carried out were professional and made a vast improvement to the site. |  | 27.6.16 | Closed
21.6.16 | 11. COMPLIMENTS | Castle Place Sports centre | Gym Air conditioning | Compliments received from sites general manager wishing to express his thanks in the way the engineers completed the work on an open operational site with the minimum disruption and leaving the site clean and tidy. |  | 27.6.16 | Closed
26.7.16 | .7. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard has confirmed this will be completed in house. | IG | 23.9.16 | Closed
26.7.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side - Greg to forward list of item to be cover to Phil | Staff meeting/Phil | 14.9.16 | Closed
23.8.16 | .0. H&S | Marlborough Leisure Centre | Phil had received a report for a near miss, at this time further details are required Phil to investigate and report findings to Kier. | Phil had received a report for a near miss, at this time further details are required Phil to investigate and report findings to Kier. | Phil | 14.9.16 | Closed
23.8.16 | .1. PPM | General | Update - PPM Planner for all sites is still ongoing. It was also suggested Asset Tagging take place by independent company to spend up the process, Greg to supply costing, Phil to then liaise with Kevin regarding supplied costs and how to proceed. | Update - PPM Planner for all sites is still ongoing. It was also suggested Asset Tagging take place by independent company to spend up the process, Greg to supply costing, Phil to then liaise with Kevin regarding supplied costs and how to proceed. | Greg/Phil | 14.9.16 | Closed
23.8.16 | .2. REACTIVE | General | Paul B advised 'Fabric' works are being allocated to M & E, (samples given to Liza). WC helpdesk to be advised. It was also noted when Kier receive a SAP order the relevant lot is not noted. Liza to advise Lesley | Paul B advised 'Fabric' works are being allocated to M & E, (samples given to Liza). WC helpdesk to be advised. It was also noted when Kier receive a SAP order the relevant lot is not noted. Liza to advise Lesley | Phil/Paul | 14.9.16 | Closed
23.8.16 | .3. SUBMISSIONS | PPM | Monthly Submission | Update - Still on going as PM has again rejected a submission due to up-lift cost being applied. Submission should be re-submitted as per contract | PM | Closed | Closed
23.8.16 | .5. KPIs | General | KPIs | UPDATE still ongoing - Phil to arrange separate meeting with Kier | PB / PM | Closed | Closed
23.8.16 | .6. CONTRACTUAL | General | MT Task (Burner/Boiler) - Phil to check and report is the same or separate. | MT Task (Burner/Boiler) - Phil to check and report if MT task the same or separate. | Phil | 14.9.16 | Closed
23.8.16 | .8. CAPITAL WORKS | General | Capital works general | Capital Works Projects to be returned to requesting Project Officer/Technical Officer to place further GVAs orders if required, | Phil | 23.6.16 | Closed
23.8.16 | .1. PPM | General | Tom requested ZIP Boilers are serviced quarterly in the Hubs/ Campus due to high usage. | Tom requested ZIP Boilers are serviced quarterly in the Hubs/ Campus due to high usage. Phil agreed but costing need to be confirmed. Phil to then advise Kier accordingly. ZIP boilers in school to be discussed when to be serviced in a separate meeting. | Phil/Tom | 14.9.16 | Closed
14.9.16 | .1. PPM | All sites | PPM Planner for all sites | PM still awaiting a full planner. TS to provide a copy this week for Leisure Site, Hubs, and the History Centre, however this will be an indicative document and amendments will be required as and when assets are identified. In particular Schools. | 23.11.16 | 25.10.16 | Closed
14.9.16 | .3. SUBMISSIONS | General | Monthly Submission and cross service sectors | PB identified that there were still issues whereby works were being allocated to the incorrect lots on the order from the helpdesk. Phil requested that the GVAs orders are sent to him so the issues could be addressed. | PW/Phil | Closed | Closed
14.9.16 | .0. H&S | Marlborough Leisure Centre | Phil had received a report for a near miss, at this time further details are required Phil to investigate and report findings to Kier. | Phil had received a report for a near miss following further investigation Phil has advised no further action is required and the issue is closed . | Phil | 14.9.16 | Closed
14.9.16 | .0. H&S | General | Staff monthly Tool Box talks | Greg to forward list of item to be cover to Phil | Greg/Phil | Closed | Closed
14.9.16 | .1. PPM | General | ZIP Boilers | Delivery Managers have requested ZIP Boilers are serviced quarterly in the Hubs/ Campus due to high usage. Phil has now agreed costing regarding Hubs, concerning School Zip boiler this still needs to be confirmed. Phil to send Kez annual cost as Kez has advised the cost can be re-charged to the 3rd floor occupants at Monkton Park. | Phil/Kez | 25.10.2016 | Closed
14.9.16 | .0. H&S | General | Staff monthly Tool Box talks | Greg to forward list of item to be cover to Phil | Greg/Phil | Closed | Closed
14.9.16 | .1. PPM | General | Asset Tagging | Update - It was also suggested Asset Tagging take place by independent company to speed up the process, Greg Asked for a priority list to be provided with regards to property status and elements to be tagged in order to seek various costs. LG is working to seek an agreed list with estates | Greg/Phil/LG | 14.9.16 | Closed
14.9.16 | .1. PPM | School Sites | Update clarification required from Kier if School Servicing is up to date, as the schools have been invoiced for a whole year of servicing. Therefore is any servicing has not been carried out the school may need to be credited | Update clarification required from Kier if School Servicing is up to date as the schools have been invoiced for a whole year of servicing. Therefore is any servicing has not been carried out the school may need to be credited. Tom to investigate and advise Phil accordingly. | Tom/Phil | 23.10.16 | Closed
14.9.16 | .2. REACTIVE | General | Pete advised works are being allocated to the incorrect lots M & E, to F & S and vice a versa. Phil requested example to be sent to him so the issue can be addressed. | Pete advised works are being allocated to the incorrect lots M & E, to F & S and vice a versa. Phil requested example to be sent to him so the issue can be addressed. | Pete/Phil | 23.10.16 | Closed
14.9.16 | .6. CONTRACTUAL | General | MT Task (Burner/Boiler) - Phil to check and report is the same or separate. | Phil to arrange a separate meeting with Tom with discuss | Phil/Tom | 23.10.16 | Closed
14.9.16 | .9. SITE CHANGES | Site | Tisbury Library | To be confirmed with Darren Maplesden if this is now a void property and advise if services need to be drained down/capped off. | MW | 23.10.16 | Closed
14.9.16 | .0. H&S | General | Staff monthly Tool Box talks | Greg to forward list of item to be cover to Phil | Greg/Phil | Closed | Closed
14.9.16 | .10. EARLY WARNING NOTICE | General | KPI reporting | Phil advised that he will be raising an early warning with regards to Quality of KPI reporting | Phil/Greg | 23.10.16 | Closed
14.9.16 | .4. ENERGY | General | No action taken | No action taken | All | 23.10.16 | Closed
25.10.16 | .9. SITE CHANGES | Site | C4 & C5 Hopton Devizes | This site is now closed when services is required keys to be collected from County Hall FM Office. Mike Dawson is the lead on info for this site. | Mike Dawson | 31.01.17 | Closed
25.10.16 | .9. SITE CHANGES | Site | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodmans is leading on this project | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodman is leading on this project. | Tim Goodman | 28.02.17 | Closed
25.10.16 | .9. SITE CHANGES | Site | Little Folly Children Centre (Winding Way) UPRN 01153S2 | Closed - nursery (South hill School) are taking on the whole of the building GVAs ORDER 106689 TO BE RE-INSTATED | Anna Cox | 20.12.16 | Closed
25.10.16 | .0. H&S | General | OOH attendance | Greg advised if attendance is required OOH Kier staff will have be to be accompanied while on site. Phil advised as Blue 9 should also be on site as the key holders. | Greg/Phil | Closed | Closed
25.10.16 | .1. PPM | General | PPM Planner | Tom advised completed PPM list to be forward to Phil by the End of November - UPDATE - Planner has now been received from Tom, Liza to amend as required, planner to then be returned to Tom - end date has yet not been decided. UPDATE - Tom has been advised as there are only 3 school remaining to be added to the PPM Planner it can now be uploaded and any required amendments can made at a later date. Phil to hold separate meeting with Kevin regarding asset tagging/verification Tom advised this is very near to completion. Tom has also requested for a separate meeting to discuss issues with Pre-School, Nurseries, and Children Centre to clarify what assets are on site and need to be added to the PPM. Kier informed Wayne Robson has been given this task to visit each site, so assets could become clearer. UPDATE Tom to forward PPM planner minus Schools so that new GVA's orders can be raised for the new financial year 17/18. UPDATE: PM stressed importance of workable planner to produce KPI's for coming year. TS to supply PM list of Leisure Centres and Hubs (as looked after previously by Kier) as requested by Mon am 3rd April | Tom/Phil/Liza | Open | Open
25.10.16 | .10. EARLY WARNING NOTICE | General | No action taken | No action taken |  | 25.10.16 | Closed
25.10.16 | .6. CONTRACTUAL | General | Kevin Butcher on draft CDM responsibilities. | Kevin to update Greg accordingly, Phil to have further meeting with Kevin. Phil to liaise with Kevin to discuss having in place a formal process for the appointment of a principal contractor. UPDATE Greg highlighted CDM responsibilities could now be at risk. Phil to liaise with Kevin. UPDATE: Ongoing KB to discuss with Capital Team | Kevin/Phil | Ongoing | On-going
25.10.16 | .6. CONTRACTUAL | General | Uplift on MTC threshold. | To be discussed if threshold to be raised from £50.000.00 - amount to be agreed with Procurement. Phil to liaise with Kevin Phil has advised he has spoken to Procurement and was just waiting for a confirmation letter. Phil also advised he will be releasing several FMC works to Kier above the £50.000 threshold. Kevin has documentation which requires Barry Parrie's approval. To be discussed if threshold to be raised from £50.000.00 - amount to be agreed with Procurement. Phil to liaise with Kevin Phil has advised he has spoken to Procurement and was just waiting for a confirmation letter. Phil also advised he will be releasing several FMC works to Kier above the £50.000 threshold. Kevin has documentation which requires Barry Parrie's approval. . Phil to keep Kier updated. UPDATE Phil advised the process has now been agreed and now only waiting for WC's legal department to send acceptance letter out to Kier for signing. UPDATE: PM to chase legal/TB for official letter to Kier | Phil/Kevin | Open | On-going
25.10.16 | .8. CAPITAL WORKS | General | Capital works general | Liza advised completed list has now been sent to Education for approval. Kier advised Education have cut the budget which will impact on works to be carried out. Greg requested approved list to be forwarded when works are known. Phil to speak to KB on sending on relevant information. UPDATE Kevin has been to several meetings in which he has raised the issue of the Corporate Risk. FMC works still not being released as still require approval. Contractor advised to still check the South West Portal. Update: FMC 16/17 all orders raised and issued. DC to email Iwan to confirm any 16/17 outstanding works. CMA 17/18 Projects list sent to Kier (Indicative). Scope of works to be clarified and priced. Site meetings being held with WR for clarification. UPDATE Site visits have now been completed and costed, with order now being placed. FMC works now have to be approved via the 'gateway. excepted approval dates middle of June. | Phil | Open | On-going
25.10.16 | .3. SUBMISSIONS | Schools Site | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. Paul advised staff have been allocated to clear back log of O/S work orders. Kier again advised to prioritise schools as they are chasing when they will be invoiced. Figure received show that there are still 832 fabric works orders to be invoiced. Greg advised staff were still working to clear backlog. Phil to arrange separate meeting in January 2017 on how to clear backlog of outstanding invoices for Schools UPDATE Phil to formally write to Kier requesting a completion date. Phil to also discuss the issue with the o/s invoices for schools with Kevin. | Paul/Greg | 30.05.17 | Closed
25.10.16 | 10. COMPLAINTS | general | Non reported | No Action Required |  | Closed | Closed
25.10.16 | .2. REACTIVE | General | Z1 reports. | Phil to arrange a separate meeting with Greg to discuss re-occurring issues | Phil/Greg | 22.11.16 | Closed
22.11.16 | .10. EARLY WARNING NOTICE | General | No action taken | No action taken |  | 22.11.16 | Closed
22.11.16 | .2. REACTIVE | School Site | Greentrees Junior School - de-commissioning of lift | Andrea to liaise with Tom as the school require pricing to de-commission a lift on site. UPDATE Tom is still waiting for Andrea to supply details of type, make of lift before producing costs. | Andrea/Tom | 22.11.16 | Closed
22.11.16 | .4. EARLY WARNINGS | General | No action taken | No action required |  |  | Closed
22.11.16 | .8. CAPITAL WORKS | General | Capital works general | Phil advise some pre-measure works have now been release site included Amesbury Leisure Gym works (Andrea waiting for costs). Olympiad Leisure, tank works, lift and soffit works. Bradford on Avon chemical stores. Phil to keep Kier updated. Phil to keep Kier updated with further meeting to be arrange in January 2017 UPDATE Phil advised approval had now been received for additional works to be carried out with orders being raised by the end of March. UPDATE: Westbury Pool Door to be completed 28.03.17. | Phil | 30.05.17 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01400S1 | Bowerhill Melksham PDC Lancaster Road SN12 6SP | Site has now been sold can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01067S3 | Corsham Regis Children Centre SN13 0EG | CLOSED - nursery (South Hills) are taking over whole building can be removed from PPM Planner GVAs ORDER 106588 TO BE RE-INSTATED |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01121S2 | Malmesbury Children centre SN16 9JR | CLOSED - premises will be handed back to school can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 40035S1 | Corner House Children's Centre George Lane CP Marlborough SN8 4BY | Site is closed can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01610S2 | Five Wishes Children's Kitchener Road Amesbury SP4 7AA Centre | CLOSED - nursery (Smiley Faces) are taking over whole building. Can be removed from PPM Planner GVAs ORDER 106679 TO BE RE-INSTATED |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01655S1 | Wilton Children's Centre ( West Street Wilton SP2 0DL | CLOSED - vacant - notice has been served to terminate the lease. Can be removed from PPM Planner |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01557S1 | Ludgershall YC, Andover. SP11 9LZ | This site is now void and all services have been isolated and drained down , all works to be put on hold as advised by John Price. Keys held in the FM key cabinet, hook 72 BH | John Price | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 30007S2 | The Barn Penny farthing - Salisbury SP1 | Remove from PPM planner as this site is part of PF House which has now been sold. QFM 149584 (No GVAs order has been placed) |  | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01008S1 | The John Ivie Centre (Exeter House) | Remove from PPM planner, WC have no responsibilities for this site as advised by John Price/Mark Murnane QFM 150197 (No GVAs order has been placed) |  | 20.12.16 | Closed
22.11.16 | 10. COMPLAINTS | general | Longford Primary School | Andrea received a complaint from the school regarding the school being flooded after works carried out by engineer on the TMV's. Pete advise the issue had now been resolved. | 22.11.16 | Closed | Closed
22.11.16 | 11. COMPLIMENTS | Larkhill Primary School | Andrea had received a compliment for Kier engineer Chris Bradshall on his workmanship. | Andrea had received a compliment for Kier engineer Chris Bradshall on his workmanship. | Andrea | 22.11.16 | Closed
22.11.16 | .2. REACTIVE | School Sites | Andrea had received several calls from school site to report that appointments were not being made from contractors. Paul confirmed contractor were aware this was procedures, and would re-iterated procedures to both subcontractors and Kier engineers | Andrea had received several calls from school site to report that appointments were not being made from contractors. Paul confirmed contractor were aware this was procedures, and would re-iterated procedures to both subcontractors and Kier engineers | Andrea/ Paul | 22.11.16 | Closed
20.12.16 | .0. H&S | Bourne Hill Salisbury | Aria Engineer having to gain access to plant room through roof hatch. | Mark advised the Aria engineer had difficulties gain access through the roof hatch to the top plant room. Mark to liaise with Corporate Health, on how to proceed. Greg also advised a Risk Assessment is required to be carried out by all attending engineers on safety when entering confined spaces. | Mark | 20.12.16 | Closed
20.12.16 | .10. EARLY WARNING NOTICE | General | No action taken | No action taken |  | 20.12.16 | Closed
20.12.16 | .2. REACTIVE | Bourne Hill Salisbury | Emergency Lighting throughout the building | Mark advised there were approx 108 none working EM lights throughout the building. Most of the works will be required to be carried out OOH as some of the works will be at high level. Mark is also liaising with Corporate Health about the situation on site. | Mark | 31.01.17 | Closed
20.12.16 | .4. EARLY WARNINGS | General | No action taken | No action required |  |  | Closed
20.12.16 | .6. CONTRACTUAL | General | Social Values | Phil advised regarding the Social Values this has now been postponed and will again be reviewed in the new year. | Phil | 20.12.16 | Closed
20.12.16 | .0. H&S | General | Staff monthly Tool Box talks | Paul confirmed these are still taking place monthly and issues also discussed has been the added value the engineers can bring to the contract, i.e. how they present themselves when on site. | Paul | 20.12.16 | Closed
31.01.2017 | .0. H&S | Amesbury Sports Centre | Removal of tank | Pete advised due to the confined space for the removal of the tank it is excepted that there would be a presence of asbestos, therefore the appropriate steps will be taken before works commence. UPDATE Pete advised a process had now been put in place. | Pete/Phil | 31.01.17 | Closed
31.01.2017 | .2. REACTIVE | County Hall | Lighting System in County Hall | Pip asked if the issues with the lighting system in CH could be resolved with the showing faults being removed. Tom advised due to the nature of the system the issues could not be resolved, but he did suggest that a dead man switch could be fitted to cover the whole building, Pete to supply cost for Pip. | Pet/Pip | 31.01.17 | Closed
31.01.17 | .5. KPIs | General | KPIs | Phil to keep monitoring KPI performance due to Kier now reducing resources, which could have impact on KPI figures | PB / PM | 28.02.17 | Closed
31.01.17 | 11. COMPLIMENTS | County Hall Trowbridge | Lighting Engineers | Pip complimented the Kier engineers for their performance with regards to the issues with the lighting issues within County Hall | Pip | 31.01.17 | Closed
31.01.17 | 11. COMPLIMENTS | Various sites | T H White Engineers | Pip complimented the TH White engineers for ringing the FM Support Line for site access information and for not just arriving at site. | Pip | 31.01.17 | Closed
31.01.17 | 10. COMPLAINTS | Marlborough Leisure Centre | AHU | Complaint received with regards to the misdiagnosis of a failed AHU which caused inconvenience to both customers and site staff. Following investigation this has not been reported back and the matter closed. | Paul B | 31.01.17 | Closed
28.02.17 | .0. H&S | General | Issue raised by Kier | Tom advised after a Kier audit meeting the issue was highlighted that WC should supply the Statutory Inspection Reports supplied from Zurich Insurance covering the last 12 months. Phil to speak to John Bolton as these are sent to him and John then actions them accordingly. UPDATE: chase JB for last 12 months of Zurich reports | Tom. Phil John Bolton | 28.03.17 | Open
28.02.17 | .0. H&S | General | Issue raised by Kier | Tom advised after a Kier audit meeting the issue was highlighted that WC should supply Risk Assessments for all WC buildings. Tom informed when Concerto goes live these documents should then be available to see. | Phil | 28.03.17 | Closed
28.02.217 | .1. PPM | Preschool, Nurseries, Children Centre | PPM Planner | Tom has requested the completed asset sheets are in the same format as were completed for the schools Tom can then ensure correct sites and assets are added to the planner. TS is still waiting for a list for asset verification | Liza | 30.05.17 | Closed
28.02.217 | .1. PPM | General | PPM Planner | Tom advise that there were still outstanding remedial works not completed from a service visit. Tom to send list of required remedial to be carried out to the Hard FM Team who will then chase the appropriate persons. | Liza/Mo | 30.05.17 | Closed
28.02.17 | .0. H&S | General | Kitchen Equipment and C02 levels | Tom raised the issue, sites with kitchen equipment in should have a process in place regarding C02 levels. Phil to liaise with Paul Collier to discuss if documentation needs to be sent to relevant sites. UPDATE: PM to liaise with Paul Collyer for draft letter to schools (if have gas cookers to service and have adequate levels of ventilation). Simon Toomey to assist with letter | Phil | 28.03.17 | Closed
28.02.17 | .5. KPIs | General | KPIs | Phil advised there has been an improvement in the KPI figure. Phil to arrange a separate meeting to discuss the impact that pre-measure, estimate budgets and 10 day + open orders are having on the KPI figures. | PB / PM | Open | Open
28.03.17 | .0. H&S | General | Confined Spaces | Kier requested list of confined spaces. PM advised that WC do not have a list and Kier need to compile a list from engineers. TS to arrange meeting to compile with PM | Tom/Phil | 28.04.17 | Closed
28.03.217 | .1. PPM | General | Works from Service | TS has added tab to KPI report of outstanding works from service visits that have not been actioned | TS | Ongoing | Closed
28.03.17 | .2. REACTIVE | General | Issues Log | PM to forward Kier issues log to be updated on reactive jobs | Pete Wort | 28.04.17 | Closed
29.03.17 | .3. EARLY WARNING | General | Early warnings | Kier issued No 4 re: Audit Process. PM established there is a process and will adapt it to fit | Phil | Open | Closed
29.03.17 | .5. CONTRACTUAL | General | Organisational Structure | PB provided organisational chart but PM requested official notification of Senior Change in Management. Still waiting | PB | 30.04.17 | Closed
29.03.17 | .5. CONTRACTUAL | General | Sub Contractors | PM still waiting for documents. TS to provide in GJ absence | Tom | 30.04.17 | Open
28.03.17 | .0. H&S | General | Staff monthly Tool Box talks | Continues with Engineers who receive handouts and give feedback to highlight issues | Kier | 28.04.17 | Closed
29.04.17 | .9. SITE CHANGES | UPRN 01697S1 | The Big Shed Folly Road Devizes | Handed back to the Landlord on the 29/04/2017. This property in avoid Permanent Void – building empty and not to be re-occupied | Transferred back to the landlord 29/04/2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 01406S1 | Warminster Youth Development Centre, The Wave, The Close, Warminster BA12 9AL | Now under the remit of the Parochial Church Council of Christ Church Youth Club. No longer WC Responsibility | Open | 01 .04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 40010S1 | Devizes Couch Lane, 7 Couch Lane, Devizes SN10 1EB | Lease Out to Guy’s Magnets Ltd | Open | 31.03.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30057S1 | Salisbury Fisherton Clock Tower | SOLD to Salisbury City Council | Open | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30022S2 | Salisbury Culver Street PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Open | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30026S2 | Salisbury Millstream Approach Coach Station PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | (UPRN 30017S2) | Shopmobility, The Maltings, Salisbury SP2 7TL | Shopmobility, The Maltings, Salisbury SP2 7TL has now been transferred to Salisbury City Council with effect from 1st April 2017 | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 10044S2 | Chippenham Bath Road Public Conveniences | Now under the remit of Chippenham Town Council 20/04/2017 | Handed over to Chippenham Town council from the 20/04/2017 | 20.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 01697S1 | Devizes Folly Road Warehouse (Big shed) | Lease has now been terminated 29/04/2017 | Lease has now been terminated 29/04/2017 | 29.04.2017 | Open
30.05.17 | .2. REACTIVE | County Hall | County Hall - non working lift | Peter advised the lift was still not working and the issue was with the UPS batteries not charging. A Kier engineer was liaising with a company in Bristol however it was suggested that a new UPS may be required. | Pete/Phil | 30.05.17 | Open
30.05.17 | .2. REACTIVE | All Hub Buildings | ZIP Boilers | This is the ongoing issue with ZIP boilers within the HUBS breaking down. Tom advised this is due to over usage. Pete to arrange for Kier engineer to have attend a training from course from 'ZIP' . Greg also suggested that WC Foo;'s also have training , Phil advised against this. | Pete/ Phil | 30.05.17 | Open
30.05.17 | 10. COMPLAINTS | General | Various issues | Greg advised following a reported 4 complaints, all issues had been a result of a communication breakdown between Kier staff and WC staff. Phil and Greg to re-iterate to staff about adding messages to Concerto and QFM.. | Greg/ Phil | 30.05.17 | Closed
30.05.2017 | .1. REACTIVE | General | General | Kier to produce a WIP (works in progress) and a JIP (Jobs in progress) reports. This is to be an interim process until Kier new system Concept is completed and live by the end of September. Phil and members of Kier will have weekly meetings (Tuesdays) to discuss any outstanding issues. Vincent showed Kier the Suppliers Portal on Concerto were job status information can exported to by Kier. | Kier/Phil | 30.05.17 | Open
30.05.2017 | .1. REACTIVE | General | Blue 9 and Kier OOH Service | Phil advised several issue had been raised that when Blue 9 call Kier OOH that no reference no is given and some call are taking up to an hour to be answered. Greg advised once a call is received a reference no is automatically produced. Greg to request reports from the OOH support line which will show required details. Phil advised Kier to liaise with Sarah Peters as the Blue 9 contract fall under her remit. | Kier/Phil | 30.05.17 | Open

## FIRE & SEC (hidden)
| LOT 4 | FIRE & SECURITY | MONTHLY MAINTENANCE CONTRACT MEETINGS
| DATE | 2017-05-30
| ATTENDEES | Phil McMullan (WC) MaureenWells (WC) Tom Somerville (Kier) Pete Wort (Kier) Greg Jones (Kier) Vincent Albano (WC)
| APOLOGIES | Paul Bramhall (Kier) Liza Gordon (WC)
| MT | Liza Gordon
DATE Example 26.4.16 | AGENDA CATEGORY | SITE / LOCATION / GENERAL | BRIEF DESCRIPTION | COMMENTS | PERSON TO ACTION | DATE TO BE ACTIONED BY | STATUS
.0. H&S
.1. PPM
.2. REACTIVE
.3. SUBMISSIONS
.4. EARLY WARNINGS
.5. KPIs
.6. CONTRACTUAL
.7. ENERGY
.8. CAPITAL WORKS
.9. SITE CHANGES
10. COMPLAINTS
11. COMPLIMENTS
26.4.16 | .1. PPM | General | Tom S advised on some sites attended by previous contractor fobs were now not working, (Kennet house) | Possible WC access code or unique engineer code may be required to all access systems. | Tom Somerville | Ongoing | Closed
26.4.16 | .0. H&S | General | Site to show evidence of weekly Testing being carried out on alarm systems | Kier Engineers to monitor | Kier | 14.9.16 | Closed
26.4.16 | .0. H&S | General | TH White to attend induction courses | Required for new employees | Kier | 14.9.16 | Closed
26.4.16 | .3. SUBMISSIONS | General | 3rd week of every month |  | Mo | 24.5.16 | Closed
26.4.16 | .4. EARLY WARNINGS | General | Greg Jones raised early warning due to documentation impact not being loaded onto Concerto |  | Greg Jones | 24.5.16 | Closed
26.4.16 | .5. KPIs | General | KPI's to be sent before next meeting so any issues can be raised. | To be sent to Phil | Phil Mc | 24.5.16 | Closed
26.4.16 | .8. CAPITAL WORKS | General | Kier advised to check the south West Portal |  | Kier | 24.5.16 | Closed
26.4.16 | .2. REACTIVE | General | No actions reported. | No Action | Kier | Ongoing | Closed
26.4.16 | .9. SITE CHANGES | General | Kier to be informed of any changes to site e.g.. voids, or no longer WC responsibility | Mo/Liza to advise accordingly | Mo/Liza | 24.5.16 | Closed
26.4.16 | .6. CONTRACTUAL | General | Costings to be produced for Fire Alarms - Cost per area/cost up to 40 items. To be agreed price of £1.50 per item. | Phil to liaise with Tom as to ''what is an item'' | Phil Mc/Tom S | 24.5.16 | Closed
26.4.16 | .6. CONTRACTUAL | General | Phil to liaise with Kevin Butcher on draught CDM responsibilities. | Phil to speak to Kevin | Phil Mc/Kevin B | 24.5.16 | Closed
26.4.16 | .7. ENERGY | General | Non received | No Action |  | 26.4.16 | Closed
26.4.16 | 10. COMPLAINTS | General | Non received | No Action |  | 26.4.16 | Closed
26.4.16 | 11. COMPLIMENTS | General | Non received | No Action |  | 26.4.16 | Closed
24.5.16 | .0. H&S | General | Testing being carried out on alarm systems | Site to show evidence of weekly testing reports. | Site | 14.9.16 | Closed
24.5.16 | .1. PPM | Statutory servicing only being carried out. | Statutory servicing only being carried out from previous contractors planners. Documentation to be added to QFM | Tom Somerville | Ongoing | 21.6.16 | Closed
24.5.16 | .2. REACTIVE | General | M/&E and Fire & Security lots on GVAs | When order being placed by WC Helpdesk F & S is being allocated to M&E. Phil to liaise with helpdesk. | Phil | 21.6.16 | Closed
24.5.16 | .2. REACTIVE | General | Emergency 2hrs - GVAs orders. | To be monitored if actually a emergency and if attendance required with 2hrs | Phil/Kier | 21.6.16 | Closed
24.5.16 | .3. SUBMISSIONS | General | 3rd week of every month | Mo to process PPM submission as required corresponding documentation located in QFM | Mo | 21.6.16 | Closed
24.5.16 | .5. KPIs | General | KPI's to be sent to Phil McMullan to discuss process. | Phil and Paul to discuss in separate meeting | Phil/Paul | 25.10.16 | Closed
24.5.16 | .6. CONTRACTUAL | General | Phil to liaise with Kevin Butcher on draught CDM responsibilities. | To also be discussed further at the Contractors Quarterly Meeting | Phil Mc/Kevin B | 21.6.16 | Closed
24.5.16 | .7. ENERGY | General | Non received | No Action |  | 24.5.16 | Closed
24.5.16 | .8. CAPITAL WORKS | General | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA | Contractor advised to check South West Portal. If any works under £50.000 works will be awarded to contractor and order placed on GVA | Kier | 25.10.16 | Closed
24.5.16 | .9. SITE CHANGES | Site | Site changes | Pennyfarthing House, Salisbury - no longer WC property from the 01/07/2016.Kevin to liaise with developer if site to be decommissioned of all services. Calne Leisure Centre to be added to list from 21/06/2016 | Kevin/Phil | Closed | Closed
24.5.16 | .2. REACTIVE | General | Fire alarm break glass, alarm keys. | Tom suggested that spare break glass and keys are left onsite as site are calling in to the helpdesk with issues. Kier attend site to only replace glass/key. If sites has spare this could become a cost saving to WC. Phil to advise. | Phil | 21.6.16 | Closed
21.6.16 | .1. PPM | County Hall, Monkton Park, Bourne Hill | John Bolton - confirmation for the helpdesk when placing orders for Emergency Lighting either F & S or M & E | Phil advised the 'Helpdesk' should place orders for Emergency Lighting under M & E LOT 2 | Phil | Open | Closed
21.6.16 | .0. H&S | County Hall, Monkton Park, Bourne Hill | Kevin, Phil to liaise and to confirm with Delivery Managers of the Hubs if weekly alarm testing can be carried out by FOO's. | Kevin, Phil to liaise and to confirm with Delivery Managers of the Hubs if weekly alarm testing can be carried out by FOO's. | Phil | 14.9.16 | Closed
26.7.16 | .1. PPM | General | PPM in general | TS advised that TH white are carrying servicing as per information provided and reacting to any school identifying a missed service. | TS | Closed | Closed
21.6.16 | .2. REACTIVE | General | Fire alarm break glass, alarm keys. | John Bolton to raise order on GVAs for delivery of break glass and keys. To be delivered to each Hub's FM office so they can be sent to sites as required, | John Bolton | 24.6.16 | Closed
21.6.16 | .2. REACTIVE | Christie Miller | Fire/Intruder alarm at Christie Miller | Tom has requested costing from TH White to have the fire, intruder alarms monitored. | Tom | 23.8.16 | Closed
21.6.16 | .2. REACTIVE | General | Fire extinguishers on WC vehicles | Phil confirmed that fire extinguishers on WC vehicles should be arranged to be serviced by 'Fleet' | Phil | 21.6.16 | Closed
21.616 | .4. EARLY WARNINGS | General | Phil McMullan raised early warning notice - on not receiving PPM Planner | Phil to liaise with Greg. | Phil/Greg | 23.8.16 | Closed
21.6.16 | .5. KPIs | General | KPI's to be sent to Phil McMullan | Phil and Paul to discuss in separate meeting so targets can be met. | Phil/Paul | 22.11.16 | Closed
21.6.16 | .6. CONTRACTUAL | General | Kevin Butcher on draft CDM responsibilities. | Kevin to update Greg accordingly, Phil to have further meeting with Kevin. UPDATE Phil to liaise with Kevin to discuss having in place a formal process for the appointment of a principal contractor as UPDATE Greg highlighted CDM responsibilities could now be at risk. Phil to arrange meeting with Kevin. Matter outstanding with KevinUPDATE: Ongoing KB to discuss with Capital Team | Kevin/Phil | Ongoing | Open
21.6.16 | .8. CAPITAL WORKS | General | John Bolton advised if any site required a re-wire the works would also include an update on the fire alarm system. |  | WC | 21.6.16 | Closed
21.6.16 | .9. SITE CHANGES | Site | Tisbury Library | Re-opening at the new Tisbury Nadder Campus | Phil | 05.09.16 | Closed
21.6.16 | .9. SITE CHANGES | Site | Calne Leisure Centre (White Horse Sports Centre) | WC responsibility effective form the 21/06/2016 | Phil | 23.8.16 | Closed
21.6.16 | 10. COMPLAINTS | General | Non received | No Action |  | 21.6.16 | Closed
26.4.16 | 11. COMPLIMENTS | General | Non received | No Action |  | 21.6.16 | Closed
21.6.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advised 3 member of staff still require DBS clearance. | P Bramhall | 14.9.16 | Closed
21.6.16 | .7. ENERGY | General | Energy / carbon reduction incentive | Kier new vans are energy efficient are also fitted with tracking devices. | Greg Jones | 23.8.16 | Closed
21.6.16 | .7. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard to advise if this is to fall under the remit of the Energy Team to Kier | Phil / Ian | 23.8.16 | Closed
26.7.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side | Staff meeting | Closed | Closed
26.7.16 | .0. H&S | Toolbox Training | DBS for all staff | Paul Bramhall advise 1 staff member to be finalised on DBS | P Bramhall | Ongoing | Closed
26.7.16 | .2. REACTIVE | General | Order / Work Process | It was highlighted during the meeting that work orders were not being closed down and a new one raise in the event of parts ordering and extended time lines. Also there was not a consistency of procedures across the board. . Greg has provide a process flow chart for discussion Pm to hold a meeting next week to discuss and agree in the interim period prior to concerto. | PM / KB/ GJ | 25.10.16 | Closed
26.7.16 | .5. KPIs | General | KPIs | KPIs show a poor performance, however this is not a true reflection as it was identified that the order process being currently carried out has a major impact on results and also due to the fact that the results were not sense checked for exceptions | PB / PM | 25.10.16 | Closed
26.7.16 | .6. CONTRACTUAL | General | Trowbridge offices | It was acknowledged that there has been various difficulties in providing an expected service level through resources / location / technology at this stage of the contract. Kier has now taken processes of local premises and appointed permanent local employees to manage the contract. This will have a profound noticeable impact once training has been completed (October) and with the long awaited anticipated software, processes should have a more auditable working platform | All | 1.10.16 | Closed
26.7.16 | .7. ENERGY | General | Energy / carbon reduction incentive | Non reported | all | 25.10.16 | Closed
26.7.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side . Greg to forward list of item to be covered to Phil | Kier/Greg/Phil | 14.9.16 | Closed
26.7.16 | .2. REACTIVE | Trowbridge leisure centre | Fire Alarm | Tom raised an issue with the fire Alarms at the said site. TS to provide a cost of replacement as the system has become unreliable due to the age and difficulty in parts location | TS | 25.10.16 | Closed
26.7.16 | .3. SUBMISSIONS | General | Submission Issues | PM identified items with the incorrect up-lift applied and rejected the said items to be correctly submitted on next submission | PM | 25.10.16 | Closed
26.1.16 | .4. EARLY WARNINGS | General | Non Reported | No Action required |  | Closed | Closed
26.7.16 | .7. ENERGY | General | DEC (Display Energy Certificate) | Ian Gillard has confirmed this will be completed in house. | IG | 23.8.16 | Closed
23.8.16 | .3. SUBMISSIONS | PPM | Monthly Submission | Update - Still on going as PM has again rejected a submission due to up-lift cost being applied. Submission should be re-submitted as per contract | PM | 25.10.16 | Closed
23.8.16 | .5. KPIs | General | KPIs | KPIs show a poor performance, however this is not a true reflection as it was identified that the order process being currently carried out has a major impact on results and also due to the fact that the results were not sense checked for exceptions | Phil/Paul | 25.10.16 | Closed
23.8.16 | .0. H&S | General | Staff monthly Tool Box talks | Discussion held with regards to the importance of Sun protection working out side - Greg to forward list of item to be cover to Phil | Kier/Greg/Phil | 14.9.16 | Closed
23.8.16 | .8. CAPITAL WORKS | General | Capital works general | Capital Works Projects to be returned to requesting Project Officer/Technical Officer to place further GVAs orders if required, | Phil | 25.10.16 | Closed
14.9.16 | .0. H&S | General | Staff monthly Tool Box talks | Greg to forward list of item to be cover to Phil | Greg/Phil | Closed | Closed
14.9.16 | .1. PPM | General | Pete advised works are being allocated to the incorrect lots M & E, to F & S and vice a versa. Phil requested example to be sent to him so the issue can be addressed. | Pete advised works are being allocated to the incorrect lots M & E, to F & S and vice a versa. Phil requested example to be sent to him so the issue can be addressed. | Pete/Phil | 23.10.16 | Closed
14.9.16 | .4. EARLY WARNINGS | General | KPIs | Phil advised that he will be raising an early warning with regards to Quality of KPI reporting | Phil/Greg | 23.10.16 | Closed
14.9.16 | .1. PPM | School Sites | Update clarification required from Kier if School Servicing is up to date, as the schools have been invoiced for a whole year of servicing. Therefore is any servicing has not been carried out the school may need to be credited | Update clarification required from Kier if School Servicing is up to date as the schools have been invoiced for a whole year of servicing. Therefore is any servicing has not been carried out the school may need to be credited. Tom to investigate and advise Phil accordingly. | Tom/Phil | 23.10.16 | Closed
14.9.16 | .1. PPM | County Hall, History Centre, 3 Hubs | ADT Closed systems | Phil has requested a cost for replacing the ADT systems at The 3 Hubs and the History Centre. This is due to the high cost of maintenance and difficulties with closed protocol systems Update - -Adam L to obtain relevant plan copies of sites. UPDATE: Compiling list for 17/18 of known sites | Tom/Phil | 25.10.16 | On-going
14.9.16 | .1. PPM | Tisbury Nadder | G4S CCTV system installation at Nadder Campus. & Five Rivers Leisure Centre. | Tisbury Nadder have a monitoring system controlled by G4S. Phil advised Paul Fenning (Cardiff Commissioning) to change system to be monitored by Southern monitoring online with all other systems maintained by TH White | Tom/Phil | 20.12.16 | Closed
25.10.16 | .9. SITE CHANGES | Site | C4 & C5 Hopton Devizes | This site is now closed when services is required keys to be collected from County Hall FM Office. Mike Dawson is the lead on info for this site. | Mike Dawson | 31.01.17 | Closed
25.10.16 | .9. SITE CHANGES | Site | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodmans is leading on this project | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodman is leading on this project. UPDATE all services are on hold until further notice | Tim Goodman | 28.02.17 | Closed
|  | Site | Little Folly Children Centre (Winding Way) UPRN 01153S2 | Closed - nursery (South hill School) are taking on the whole of the building | Anna Cox | 20.12.16 | Closed
25.10.2016 | .0. H&S | General | OOH attendance | Greg advised if attendance is required OOH Kier staff will have be to be accompanied while on site. Phil advised as Blue 9 should also be on site as the key holders. | Greg/Phil | Closed | Closed
25.10.16 | .1. PPM | General | PPM Planner | Tom advised completed PPM list to be forward to Phil by the End of November | Tom/Phil | 22.11.16 | Closed
25.10.16 | .4. EARLY WARNINGS | General | No action Taken | No action Taken |  | 25.10.16 | Closed
25.10.16 | .6. CONTRACTUAL | General | Uplift on MTC threshold. | To be discussed if threshold to be raised from £50.000.00 - amount to be agreed with Procurement. Phil to liaise with Kevin UPDATE Phil has advised he has spoken to Procurement and was just waiting for a confirmation letter. Phil also advised he will be releasing several works above the £50.000 threshold. Kevin has documentation which requires Barry Parrie's approval. Phil to keep Kier updated. UPDATE Phil advised the process has now been agreed and now only waiting for WC's legal department to send acceptance letter out to Kier for signing. UPDATE: PM to chase legal/TB for official letter to Kier | Phil/Kevin | Open | On-going
25.10.16 | .3. SUBMISSIONS | Schools Site | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. | Completed works for schools to be added to submission asap, as Kier advised the School are starting to chase/request update on invoice costs. UPDATE Paul advised staff have been allocated to clear back log of O/S work orders. Kier again advised to prioritise schools as they are chasing when they will be invoiced. Figure received show that there are still 87 fabric works orders to be invoiced. UPDATE Greg advised staff were still working to clear backlog. Phil to arrange separate meeting in January 2017 on how to clear backlog of outstanding invoices for Schools UPDATE Phil to formally write to Kier requesting a completion date. Phil to also discuss the issue with the o/s invoices for schools with Kevin. | Kier/Greg/Phil | Ongoing | Open
25.10.16 | .9. SITE CHANGES | Site | Little Folly Children Centre (Winding Way) UPRN 01153S2 | Closed - nursery (South hill School) are taking on the whole of the building | Anna Cox | 20.12.16 | Closed
25.10.16 | 10. COMPLAINTS | General | Non received | No Action |  | Closed | Closed
25.10.16 | .8. CAPITAL WORKS | General | Capital works general | Liza advised completed list has now been sent to Education for approval. Kier advised Education have cut the budget which will impact on works to be carried out. Greg requested approved list to be forwarded when works are known. Phil to speak to KB on sending on relevant informationUpdate: FMC 16/17 all orders raised and issued. DC to email Iwan to confirm any 16/17 outstanding works. CMA 17/18 Projects list sent to Kier (Indicative). Scope of works to be clarified and priced. Site meetings being held with WR for clarification. | Phil | 22.11.16 | Closed
25.10.16 | .2. REACTIVE | General | Z1 reports. | Phil to arrange a separate meeting with Greg to discuss re-occurring issues | Phil/Greg | 22.11.16 | Closed
25.10.16 | .2. REACTIVE | General | Devizes Leisure Centre - Intruder alarm | Tom reported the ongoing problems with the Intruder Alarm on site. After decisions with H/S and Paul Collier it was advised an Intruder Alarm was not required and if required was the PFP responsibility. | Tom/Phil | 25.10.16 | Closed
25.10.16 | .1. PPM | Tisbury Nadder | Site handover to Kier | Phil to liaise with Mark Murnane if the building has now been handed over and now to added to the Kier PPM planner re-servicing when out of defect period. | Phil/Mark | 22.11.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01400S1 | Bowerhill Melksham PDC Lancaster Road SN12 6SP | Site has now been sold can be removed from PPM Planner | Mark Honnybun | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01067S3 | Corsham Regis Children Centre SN13 0EG | CLOSED - nursery (South Hills) are taking over whole building can be removed from PPM Planner | Anna Cox | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01121S2 | Malmesbury Children centre SN16 9JR | CLOSED - premises will be handed back to school can be removed from PPM Planner | Anna Cox | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 40035S1 | Corner House Children's Centre George Lane CP Marlborough SN8 4BY | Site is closed can be removed from PPM Planner | Anna Cox | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01610S2 | Five Wishes Children's Kitchener Road Amesbury SP4 7AA Centre | CLOSED - nursery (Smiley Faces) are taking over whole building. Can be removed from PPM Planner | Anna Cox | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01655S1 | Wilton Children's Centre ( West Street Wilton SP2 0DL | CLOSED - vacant - notice has been served to terminate the lease. Can be removed from PPM Planner | Anna Cox | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01557S1 | Ludgershall YC, Andover. SP11 9LZ | This site is now void and all services have been isolated and drained down , all works to be put on hold as advised by John Price. Keys held in the FM key cabinet, hook 72 BH | John Price | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 30007S2 | The Barn Penny farthing - Salisbury SP1 | Remove from PPM planner as this site is part of PF House which has now been sold. QFM 149584 (No GVAs order has been placed) | Mark Murnane | 20.12.16 | Closed
22.11.16 | .9. SITE CHANGES | UPRN 01008S1 | The John Ivie Centre (Exeter House) | Remove from PPM planner, WC have no responsibilities for this site as advised by John Price/Mark Murnane QFM 150197 (No GVAs order has been placed) | John Price | 20.12.16 | Closed
20.12.16 | .0. H&S | General | Staff monthly Tool Box talks | Paul confirmed these are still taking place monthly and issues also discussed has been the added value the engineers can bring to the contract, i.e. how they present themselves when on site. | Paul | 20.12.16 | Closed
20.12.16 | .2. REACTIVE | General | Warminster Leisure Centre | Phil confirmed the replacement of the fire alarm on site is now going ahead. UPDATE Tom advise works have now commenced, | Tom/Phil | 28.02.17 | Closed
20.12.16 | .2. REACTIVE | General | Replacement batteries for Fire and Intruder Alarms | Tom confirmed batteries are changed at the time of servicing. If the batteries then need to be replacement a reactive order will have to be placed on GVA. Greg has requested to see documentation from his engineer if batteries are changed for audit purposes. UPDATE: TH WHite have put process in place and engineers now take photo. TS to do dip test of selected sites | Tom | 30.05.17 | Closed
20.12.16 | .5. KPIs | General | KPI's to be sent to Phil McMullan | Phil and Paul to discuss in separate meeting so targets can be met. UPDATE Phil to keep monitoring KPI performance due to Kier now reducing resources, which could have impact on KPI figures | Phil/Paul | Open | On-going
20.12.16 | .7. ENERGY | Non received | No Action |  |  | Closed | Closed
20.12.16 | 10. COMPLAINTS | General | Non received | No Action |  | Closed | Closed
20.12.16 | 11. COMPLIMENTS | General | Non received | No Action |  | 21.6.16 | Closed
31.01.16 | .6. CONTRACTUAL | General | Appointments being made re PPM Servicing | Phil had received several reports that engineer were just arriving on site without making appointment. Tom to reiterate to engineers for PPM works appointment must be made before attending site. | Tom Somerville | 31.01.17 | Closed
31.01.17 | 11. COMPLIMENTS | Various sites | T H White Engineers | Pip complimented the TH White engineers for ringing the FM Support Line for site access information and for not just arriving at site. |  | 31.01.17 | Closed
28.02.17 | .5. KPIs | General | KPIs | Phil advised there has been an improvement in the KPI figure. Phil to arrange a separate meeting to discuss the impact that pre-measure, estimate budgets and 10 day + open orders are having on the KPI figures. | PB / PM | 28.02.17 | Closed
28.02.17 | .8. CAPITAL WORKS | General | Capital works general | Phil advise some pre-measure works have now been release site included Amesbury Leisure Gym works (Andrea waiting for costs). Olympiad Leisure, tank works, lift and soffit works. Bradford on Avon chemical stores. Phil to keep Kier updated. Phil to keep Kier updated with further meeting to be arrange in January 2017 UPDATE Phil advised approval had now been received for additional works to be carried out with orders being raised by the end of March. | Phil | Open | Closed
28.03.17 | .0. H&S | General | Confined Spaces | Kier requested list of confined spaces. PM advised that WC do not have a list and Kier need to compile a list from engineers. TS to arrange meeting to compile with PM | Tom/Phil | 28.04.17 | Open
28.03.17 | .0. H&S | General | Staff monthly Tool Box talks | Continues with Engineers who receive handouts and give feedback to highlight issues | Kier | 28.04.17 | Open
28.03.17 | .2. REACTIVE | Caravan Sites | Site Surveys Fire Cabinets | Following Site surveys by TH White & Beryl original request for Fire Cabinets to be relocated to agreed positions, KM to cancel previous orders and raise new ones to include hosts. UPDATE Tom confirmed works have now been completed. | Kim | 30.05.17 | Closed
28.03.17 | .1. PPM | General | PPM Planner | PM stressed importance of workable planner to produce KPI's for coming year. TS to supply PM list of Leisure Centres and Hubs (as looked after previously by Kier) as requested by Mon am 3rd April | Tom/Phil | 03.04.17 | On-going
29.03.17 | .3. EARLY WARNING | General | Early warnings | Kier issued No 4 re: Audit Process. PM established there is a process and will adapt it to fit | Phil | Open | Open
29.03.17 | .5. CONTRACTUAL | General | Sub Contractors | PM still waiting for documents. TS to provide in GJ absence | Tom | 30.04.17 | Open
29.03.17 | .5. CONTRACTUAL | General | Organisational Structure | PB provided organisational chart but PM requested official notification of Senior Change in Management. Still waiting | PB | 30.04.17 | Open
29.03.17 | .5. CONTRACTUAL | General | Social Values | Noted that Kier did undertake a project at Cotswold House | N/A | N/A | Open
28.03.17 | .8. CAPITAL WORKS | Melbourne House | Snagging Items | No of faults identified. Gent system/ Quote requested for Open System. £13k with John Bolton | Phil/John | 30.04.17 | Open
28.03.17 | .5. KPIs | General | KPIs | PM to put blurb. Agree to monitor 10+day and agree process | PM | 28.04.17 | Open
28.03.217 | .1. PPM | General | Works from Service | TS has added tab to KPI report of outstanding works from service visits that have not been actioned | TS | Ongoing | Ongoing
29.04.17 | .9. SITE CHANGES | UPRN 01697S! | The Big Shed Folly Road Devizes | Handed back to the Landlord on the 29/04/2017. This property in avoid Permanent Void – building empty and not to be re-occupied | Open | 29.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPR N 01406S1 | Warminster Youth Development Centre, The Wave, The Close, Warminster BA12 9AL | Now under the remit of the Parochial Church Council of Christ Church Youth club. No longer WC Responsibility | Open | 29.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPR N 40010S1 | Devizes 7 Couch Lane,7 Couch Lane, Devizes SN10 1EB | Lease Out to Guy’s Magnets Ltd | Open | 31.03.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30057S1 | Salisbury Fisherton Clock Tower | SOLD to Salisbury City Council | Open | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30022S2 | Salisbury Culver Street PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Open | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 30026S2 | Salisbury Millstream Approach Coach Station PC | Now under the remit of Salisbury City Council from the 01/04/2017 | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | (UPRN 30017S2) | Shopmobility, The Maltings, Salisbury SP2 7TL | Shopmobility, The Maltings, Salisbury SP2 7TL has now been transferred to Salisbury City Council with effect from 01/04/2017 | Transferred to Salisbury City Council 01/04/2017 | 01.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 10044S2 | Chippenham Bath Road Public Conveniences | Now under the remit of Chippenham Town Council 20/04/2017 | Handed over to Chippenham Town council from the 20/04/2017 | 20.04.2017 | Open
29.04.17 | .9. SITE CHANGES | UPRN 01697S1 | Devizes Folly Road Warehouse (Big shed) | Lease has now been terminated 29/04/2017 | Lease has now been terminated 29/04/2017 | 29.04.2017 | Open
30.05.2017 | .1. REACTIVE | General | General | Kier to produce a WIP (works in progress) and a JIP (Jobs in progress) reports. This is to be an interim process until Kier new system Concept is completed and live by the end of September. Phil and members of Kier will have weekly meetings (Tuesdays) to discuss any outstanding issues. Vincent showed Kier the Suppliers Portal on Concerto were job status information can exported to by Kier. | Kier/Phil | 30.05.17 | Closed
30.05.2017 | .1. REACTIVE | General | Blue 9 and Kier OOH Service | Phil advised several issue had been raised that when Blue 9 call Kier OOH that no reference no is given and some call are taking up to an hour to be answered. Greg advised once a call is received a reference no is automatically produced. Greg to request reports from the OOH support line which will shoe required details. Phil advised Kier to liaise with Sarah Peters as the Blue 9 contract fall under her remit. | Kier/Phil | 30.05.17 | Closed

## LEGIONELLA (hidden)
| LOT 3 | Legionella | MONTHLY MAINTENANCE CONTRACT MEETINGS
| DATE | 15.02.2017
| ATTENDEES | Jay Dibbert (Churchill's). Iwan Van Den Berg (WC) Maureen Wells (WC)
| APOLOGIES | Matt Costello (Churchills)
| MT | Maureen Wells
DATE Example 26.4.16 | AGENDA CATEGORY | SITE / LOCATION | BRIEF DESCRIPTION | COMMENTS | PERSON TO ACTION | DATE TO BE ACTIONED BY | STATUS
.0. H&S
.1. PPM
.2. REACTIVE
.3. SUBMISSIONS
.4. EARLY WARNINGS
.5. KPIs
| .6. CONTRACTUAL | Have there been any issues or occurrences that affect the contractual aspects of this contract this month, including financial, contractual or breaches.
.7. ENERGY
.8. CAPITAL WORKS
.9. SITE CHANGES
10. COMPLAINTS
11. COMPLIMENTS
03.5.16 | .0. H&S | General | Induction training for new staff | Induction training for all staff completed. |  | Closed | Closed
03.5.16 | .0. H&S | General | DBS for all staff | Confirmed all staff has DBS as required. |  | Closed | Closed
03.5.16 | .0. H&S | General | Asbestos Reports on sites | Iwan advised all site should have a Asbestos report on site. If engineer have concerns to report, a copy of the Asbestos report can then be sent. | Iwan | 25.05.16 | Closed
03.5.16 | .1. PPM | General | PPM Planner for all sites | Full overview within 6 months. | Churchill's | 2016-11-01 | Closed
03.5.16 | .1. PPM | General | PPM Planner for all sites to be added to Zeta safe | To be added approx 6 months to be completed. | Churchill's | 2016-11-01 | Closed
03.5.16 | .2. REACTIVE | General | TMV's Adjustments | Agreed with Iwan additional TMV's adjustments submitted separate to PPM, this will also included separate costings. | Iwan | 26.05.16 | Closed
| .3. SUBMISSIONS | General | Completed works spreadsheet to be sent to Iwan | Spreadsheet to show breakdown of completed items, costings, on per site. 2 x Submissions to be sent, PPM and Reactive. Date for Submission be sent for completion around the 07th of each months. | Iwan | Closed | Closed
03.05.16 | .4. EARLY WARNINGS |  | No Actions to report | No Actions to report |  | Closed | Closed
03.05.16 | .5. KPIs | General | To be formulated for approx Oct 16. | No Actions to report | Churchill's | 2016-10-01 | Closed
04.05.16 | .6. CONTRACTUAL | General | TMV's adjustment to contract. | No Actions to report | Iwan | 03.6.16 | Closed
04.05.16 |  | General | Risk Assessment for all sites to be completed. | Nothing to report | Iwan | 23.08.16 | Closed
04.05.16 |  | General | Identification and monitoring of sentinel loops | Nothing to report | Iwan | 03.6.16 | Closed
03.05.16 | .7. ENERGY | General | No actions to report | No actions to report |  | Closed | Closed
03.05.16 | .8. CAPITAL WORKS | General | No action to report | No action to report |  | Closed | Closed
03.05.16 | .9. SITE CHANGES | General | Churchill's to be informed of any changes to site e.g.. voids, or no longer WC responsibility | Mo/Iwan to advise | Mo/Iwan | Closed | Closed
03.05.16 | 10. COMPLAINTS | General | No reports | No reports |  | Closed | Closed
03.05.16 | 11. COMPLIMENTS | General | No reports | No reports |  | Closed | Closed
25.05.16 | .0. H&S | General | New staff Training | New engineer taken on board, going through H&S training | Andy | Closed | Closed
26.05.16 | .1. PPM | General | PPM Planner for all sites to be added to Zeta safe | Added 26.07.16 |  | Closed | Closed
26.05.16 | .2. REACTIVE | General | TMV adjustments and water heater adjustments | Cost of £5 agreed for TMV adjustment and £10 for water heater temperature adjustments. To commence | Jay/Andy | 26.05.16 | Closed
26.05.16 | .3. SUBMISSIONS | General | Spreadsheet needs to e in Excel format | Need full site address and spreadsheet from zetasafe to check invoicing against for KPI | Andy | Closed | Closed
26.05.16 | .4. EARLY WARNINGS |  | No Actions to report | No Actions to report |  | Closed | Closed
26.05.16 | .6. CONTRACTUAL | General | TMV adjustment and Thermostat adjustment on hot water heaters added to contract | Cost of £5 agreed for TMV adjustment and £10 for water heater temperature adjustments. To commence | Jay/Andy | June | Closed
26.05.16 | .7. ENERGY | General | New van purchased for new employee. | Replacing entire fleet. |  | Closed | Closed
26.05.16 | .8. CAPITAL WORKS | General | No Actions to report | No action to report |  | Closed | Closed
26.05.16 | .9. SITE CHANGES | General | as above
26.05.16 | 10. COMPLAINTS | General | No Reports | No reports |  | Closed | Closed
26.05.16 | 11. COMPLIMENTS | General | No reports | No reports |  | Closed | closed
26.05.16 | 12.ANY OTHER BUSINES | General | Jade has now left the company and their currently recruiting for a new administrator for the contract |  |  | Closed | Closed
26.06.16 | .1. PPM | General | Site communication | Agreed with Andy and Jay process for on site communication from Engineers | Churchill's | Closed | Closed
26.05.16 |  | General | Change to service | Has been agreed to change from 5 monthly to yearly testing of 20% of representatives | Iwan |  | Closed
26.05.16 | 12.ANY OTHER BUSINES | General | Risk assessments | The outstanding risk assessments have been started to complete in approx 2 months time. | Jay/Andy | 28.08.16 | Closed
26.05/.16 | 12.ANY OTHER BUSINES | General | Traveller sites | Await resolution on Traveller sites and compliance. Now resolved the offices will be treated as commercial and the accommodation as domestic with Adhoc visits arranged when inspection required, | Iwan | Closed | Closed
26.05.16 | .6. CONTRACTUAL | General | Principal loops | Principle loop explained and Andy to supply a spreadsheet with a site list of sites that maybe effected and an enhanced risk assessment required to identify subordinate loops. | Andy/Iwan | Closed | Closed
26.06.16 |  |  |  | Meeting cancelled due to personal injury | Iwan | Closed | Closed
26.07.16 | .0. H&S | General | Nothing to report |  | Iwan | Closed | Closed
26.07.16 | .2. REACTIVE | General | Tanks | Tank repairs and cleaning to include all tank fly traps sit with encompassed |  | 25.10.16 | Closed
26.07.16 | .3. SUBMISSIONS | General | Spreadsheet | Now being attached to invoices | Andy | Closed | Closed
26.07.16 | .4. EARLY WARNINGS |  | No Actions to report | No Actions to report |  | Closed | Closed
26.07.16 | .5. KPIs | General |  | Still awaiting plan |  | Closed | Closed
26.07.16 | .6. CONTRACTUAL | General | Principal loops | Spreadsheet supplied needs to be reviewed, need to confirm going forward with Kevin & Wiltshire's approach. | Andy/Iwan | 25.10.16 | Closed
26.07.16 | .7. ENERGY | General | Nothing to add |  |  | Closed | Closed
26.07.16 | .8. CAPITAL WORKS | General | No Actions to report | No action to report |  | Closed | Closed
26.07.16 | .9. SITE CHANGES | General | as above | Weekly communications continue | Iwan | 25.10.16 | Closed
26.07.16 | 10. COMPLAINTS | General | No Reports | No reports |  | Closed | Closed
26.07.16 | 11. COMPLIMENTS | General | No reports | No reports |  | Closed | Closed
26.07.16 | 12.ANY OTHER BUSINES | General | Traveller sites | Traveller sites now resolved sites split into to domestic and commercial, we will test on commercial side and complete adhoc tests on the domestic as require. | Iwan | Closed | Closed
26.07.16 | 12.ANY OTHER BUSINES | General | Yearly inspections of risk assessments | Year risk assessments reviews to commence, need update. Jay advised a dedicated engineer has now been appointed to carry out WC Risk Assessments - UPDATE Jay advised programme is now coming together and 128 sites have been recognised with the programmes expected to be competed by end of January 2017 | Jay/Andy | 2017-03-01 | Closed
26.07.16 | 12.ANY OTHER BUSINES | General | Andy to revise loop costs | Principle loop list was incorrect and costs need to be supplied. This has now been passed from Andy to Matt. Matt to now liaise with Iwan. UPDATE This is to be reviewed as all sites with loops need to be identified. Iwan advised due to budgets loops will not be added to the programme until the new financial year. | Jay/Andy | 2017-04-01 | Open
23.08.16 | .0. H&S | General | Access to Westbury Leighton sport centre tank dangerous to access unable to access it safely | Discussion had around safe access with ladders , towers, but unable to find safe access method, this tank maybe not inspected this year. | Iwan | Closed | Closed
28.08.16 | .3. SUBMISSIONS | General | Invoice corroboration still an issue for Carolyn, training had on submission and cross checking invoice. | Training had issue resolved | Andy | Closed | Closed
23.08.16 | .4. EARLY WARNINGS |  | Nothing to report | No Actions to report |  | Closed | Closed
23.08.16 | .5. KPIs | General | Full service history not available yet | Widget now on my dashboard, will enter KPI's this month | Iwan | Closed | Closed
23.08.16 | .1. PPM | General | Access to schools | Refused access to schools over the summer break directly affecting compliance. Iwan has requested a list of schools where entry was refused as if appointments had been made the schools will be recharged. | Iwan/Andy | 13.12.2016 | Closed
23.08.16 | .9. SITE CHANGES | General | Residence | Agreed that caretakers and cemetery bungalows would be treated as domestic and only yearly checks done. | Iwan/Andy | Closed | Closed
26.08.16 | 12.ANY OTHER BUSINES | General | Next Meeting to held in October | Move to Bi monthly meetings | Iwan/Jay | Closed | Closed
25.10.16 | .9. SITE CHANGES | Site | C4 & C5 Hopton Devizes | This site is now closed when services is required keys to be collected from County Hall FM Office. Mike Dawson is the lead on info for this site. | Mike Dawson | 15.02.2017 | Closed
25.10.16 | .9. SITE CHANGES | Site | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodmans is leading on this project | Malmesbury Cotswold House Youth Development Centre UPRN 01622S1 Closed for refurbishment from the Friday 30th September 2016. Tim Goodman is leading on this project. | Tim Goodman | 15.02.2017 | Closed
25.10.16 | .9. SITE CHANGES | Tisbury Library (UPRN 01287S1) | Old library is now closed to be removed from asset list and PPM planner | Old library is now closed to be removed from asset list and PPM planner | Iwan | 13.12.16 | Closed
25.10.16 | .0. H&S | Various site | Churchill reported positive Legionella readings at Downland School, Westbury White Horse CC, and Oxenwood Education Centre. Also a report coliform at Fitzmaurice School. | Churchill reported positive Legionella readings at Downland School, Westbury White Horse CC, and Oxenwood Education Centre. Also a report of coliform at Fitzmaurice School. Jay advised all required works had been now carried out and the situations were under control at all the site involved and were no longer at risk. | Iwan/Jay | 25.10.16 | Closed
25.10.16 | .0. H&S | Leighton Leisure Centre | Access to storage tanks | Jay advised his engineers had reported problems with gaining access to the storage tanks. Matt C advised he will be attending site to access the problem and report his findings to Iwan | Matt/Iwan | 13.12.2016 | Closed
25.10.16 | .1. PPM | Chirton Primary | Incorrect information supplied on the amount on TMV's on site | John Bolton was concerned on the amount of discrepancies there were on the reported amount to TMV's quoted to the school. Jay advised this had been a spreadsheet entry error but the issue had now been resolved and correct figures given, and a new asset list to be sent to Iwan | John | 13.12.16 | Closed
25.10.16 | .1. PPM | North Bradley School | Incorrect information supplied on the amount on TMV's on site | Adam Leitch was concerned on the amount of discrepancies there were on the reported amount to TMV's quoted to the school. Jay advised this had been a spreadsheet entry error but the issue had now been resolved and correct figures given, and a new asset list to be sent to Iwan | Adam | 13.12.16 | Closed
25.10.16 | .0. H&S | General | Toolbox talks to be arranged with engineers | Matt C advised he will now be holding regular toolbox talks with engineers. | Matt/Iwan | 13.12.2016 | Closed
25.10.16 | 12.ANY OTHER BUSINES | General | Churchill to arrange meeting with Kier | Churchill to arrange meeting with Kier to discuss a why of working together as Churchill have the monitoring contract and Kier the servicing/maintenance contract. UPDATE Jay and Matt have had a meeting with Kier regarding the servicing/maintenance contract this is to be reviewed again in April when then TWC contract with Kier is up for renewal. | Jay/Kier | 15.02.2017 | Closed
25.10.16 | .3. SUBMISSIONS | General | No action to report | No action to report |  | Closed | Closed
25.10.16 | .4. EARLY WARNINGS |  | Nothing to report | No Actions to report |  | Closed | Closed
25.10.16 | .5. KPIs | General | Iwan to arrange further meeting to discuss KPI target. | Iwan to arrange further meeting to discuss KPI targets. Churchill KPI averaging 90%, Iwan would like to see an increase to 97% UPDATE Jay has advised that with the changes excepted to be carried out on Zetasafe this will reflect a more accurate figure with KPI's showing 98% Evidence of this to be given to Iwan UPDATE KPI's now raised to 95% . Jay advised this should improve with the data cleansing with incorrect data removed from Zetasafe. 21/03/17 Target of 96.77 achieved. | Iwan/Jay | Closed | Closed
25.10.16 | .6. CONTRACTUAL | General | Iwan requested costing for Weekly flushing | Iwan requested costing for flushing, when agreed with Procurement it can then added to the contract. - UPDATE Jay to send information to Iwan | Jay/Iwan | 15.02.17 | Closed
25.10.16 | .7. ENERGY | General | Local Engineer has now been employed, therefore cutting fuel/travelling costs | Local Engineer has now been employed, therefore cutting fuel/travelling costs |  | 25.10.16 | Closed
25.10.16 | .8. CAPITAL WORKS | General | No Actions to report | No action to report |  | Closed | Closed
25.10.16 | 11. COMPLIMENTS | General | No reports | No reports |  | Closed | Closed
25.10.16 | 10. COMPLAINTS | General | No Reports | No reports |  | Closed | Closed
25.10.16 | .0. H&S | Schools Site | Legionella training to be arranged with schools | Legionella training to be arranged with schools as they are now the budget holders the responsibility of carry out the required testing should sit with either Site Manager/ Head Teacher. The Corporate Health Team (Paul Collier) will also be sending out a corresponding letter of schools responsibilities. | Matt/Iwan | Open | Closed
25.10.16 | .6. CONTRACTUAL | General | Jay advised Chorifiers with drain valves should also be added to contract | Jay advised chorifiers with drain valves and inspection hatches should also be added to contract. Iwan to liaise with Jay in separate meeting. UPDATE Iwan has advised Chorifiers with drain valves should be added to the Risk Assessments. | Jay/Iwan | 15.02.17 | Closed
25.10.16 | .2. REACTIVE | BOA Fitzmaurice School | Re-lining of tanks | GVAs order 104191 was raised for works to carried out during the summer holiday. No work were carried out. JB has now cancelled the order as he is now getting quotations for replacement tanks and booster sets. | John | 13.12.16 | Closed
21.03.17 | .0. H&S | General | Toolbox talks to be arranged with engineers | Matt C advised he will now be holding regular monthly toolbox talks with engineers. Matt to send a programme of toolbox issues to be discussed to Iwan Monthly tool box talsk continue. | Matt/Iwan | Open | Open
13.12.16 | .0. H&S | School Site | Downland Special School | The recent legionella issue has now been resolved and all remaining remedial works to be completed W/E 16/12/2016 UPDATE Jay advised the site was still under review due to having symmetric contamination still on site. Jay has arrange a re-visit . Costing for any remedial works to be sent to Iwan. Iwan to advise site to carry out weekly flushing. | Matt/Iwan | Open | Open
13.12.16 | .1. PPM | General | No issues to report | No issues to report | Iwan | 13.12.16 | Closed
13.12.16 | .2. REACTIVE | Leisure Centre Site | Remaining works to be completed OOH as agreed with site managers | Remaining works to be completed OOH as agreed with site managers | Matt | 13.12.16 | Closed
13.12.16 | .2. REACTIVE | White Horse Leisure Centre Site | Chemical Dosing | Matt advised that chemical dosing is managed by staff on site, | Matt | 13.12.16 | Closed
13.12.16 | .3. SUBMISSIONS | General | No action to report | No action to report |  | Closed | Closed
13.12.16 | .4. EARLY WARNINGS |  | Early Warning Notice | The issues from the Early Warning Notice has now been resolved |  | 13.12.16 | Closed
13.12.16 | .7. ENERGY | General | No actions to report | No actions to report |  | 13.12.16 | Closed
13.12.16 | .8. CAPITAL WORKS | General | No Actions to report | No action to report |  | Closed | Closed
13.12.16 | .9. SITE CHANGES | Site Changes | No site changes to report | No site changes to report | Mo/Iwan | 13.12.16 | Closed
13.12.16 | 10. COMPLAINTS | General | No Reports | No reports |  | Closed | Closed
13.12.16 | 11. COMPLIMENTS | Owenwood Outdoor Centre | Iwan had received comments from Ed Plank Site Manager | Ed Plank site Manager for Oxenwood had reported that he had been impressed with both the speed and response from Churchill's engineers |  | 13.12.16 | Closed
13.12.16 | 12.ANY OTHER BUSINES | School Site | Legionella Compliance Accreditation 1 day awareness course. | A one day training course to be arranged via Iwan - dates to be confirmed in March. All schools have been invited. Closing date for sites attending the course is the 27th Jan. Jay advised to make the course cost effective attendees had to be more then 10. UPDATE Jay advised there were still several schools that had not signed up for the training course. Jay to forward list to Iwan who will then send out a reminder. Training now completed | Iwan/Jay | 21.03.17 | Closed
| .1. PPM | General | No issues to report | No issues to report |  | 15.02.17 | Closed
15.02.17 | .2. REACTIVE | General | No action to report | No action to report |  | 15.02.17 | Closed
15.02.17 | .3. SUBMISSIONS | General | No action to report | No action to report |  | Closed | Closed
15.02.17 | .4. EARLY WARNINGS |  | No Actions to report | No Actions to report |  | Closed | Closed
15.02.17 | .6. CONTRACTUAL | General | No Actions to report | No Actions to report |  | 15.02.17 | Closed
15.02.17 | .7. ENERGY | General | No actions to report | No actions to report |  | 15.02.17 | Closed
15.02.17 | .8. CAPITAL WORKS | General | No Actions to report | No action to report |  | Closed | Closed
15.02.17 | .9. SITE CHANGES | Site Changes | Melksham Football/Rugby Club | Iwan to send asset details to Jay for the now open Melksham Football/Rugby Club. | Iwan | 21.03.17 | Closed
15.02.17 | 10. COMPLAINTS | General | No Reports | No reports |  | Closed | Closed
15.02.17 | 11. COMPLIMENTS | KPI's | 95% achieved on KPI's | Iwan congratulated Jay in the raised KPI figures. |  | 15.02.17 | Closed
15.02.17 | 11. COMPLIMENTS | School Site | Following the school open days meetings | Iwan advised he had received positive feed back from schools that had attended these meeting, this had also resulted in more schools signing up for the I day course for the Legionella Compliance Accreditation Awareness training. |  | 15.02.17 | Closed
21.03.17 | 12.ANY OTHER BUSINES | Operation manual | Cost of Operation manual now supplied | Submitted for decision to be made | Kevin/Vincent |  | Open
21.03.17 | .3. SUBMISSIONS | General | End of year submission | Reminded of GVA close down at end of year and request early submission | Matt/Katie |  | Open
21.03.17 | 11. COMPLIMENTS | County hall and Monkton Park | Tank Cleans | Completed to a high standard without disruption to day to day running | Iwan |  | Open
21.03.17 | .6. CONTRACTUAL | Generally | Churchill to commence with subcontract to Kier | To start begining of April | Jay | 4.17 | Open

## ASBESTOS
| Lot 5 | Asbestos | MONTHLY MAINTENANCE CONTRACT MEETINGS
| DATE | 14.01.2020
| ATTENDEES | Iwan Van Den Berg (WC) Dave Nichol, (Nichol) Maureen Wells (WC) Dean Nichol (Nichol)
APOLOGIES
| MT | Maureen Wells
DATE Example 26.4.16 | AGENDA CATEGORY | SITE / LOCATION | BREIF DESCRIPTION | COMMENTS | PERSON TO ACTION | DATE TO BE ACTIONED BY | STATUS
.0. H&S
.1. PPM
.2. REACTIVE
.3. HOUSING
.4. SUBMISSIONS
.5. EARLY WARNINGS
.6. KPIs
.7. CONTRACTUAL
28.01.19 | .8. ENERGY | New premises | Nichol has moved to new offices which are have better insulation and more efficient lighting and heating | Nichol has moved to new offices which are have better insulation and more efficient lighting and heating | Nichol | Closed | Closed
.9. CAPITAL WORKS
10. SITE CHANGES
11. COMPLAINTS
12. COMPLIMENTS
18.07.19 | 13.AOB | General | Format of Spreadsheets | Iwan waiting for a response from Dean regarding the excel format on spreadsheet and if they work e.g drop down etc. 11/09/2019 Dean has now sent spreadsheet to Iwan as requested | Iwan/Nichol | 11.09.19 | Closed
17.07.18 | .0. H&S | General | Training to be continued with regular toolbox meeting | Training to be continued with regular toolbox meeting | Nichol | 17.07.2018 | Closed
17.07.18 | .3. HOUSING | General | Nichol to continue to arrange separate meeting with Housing | Nichol to continue to arrange separate meeting with Housing | Nichol | 17.07.2018 | Closed
17.07.18 | .1. PPM | General | Nichol now inputting direct to Concerto | Nichol now inputting PPM application direct to Concert, and all parties happy with the process | Nichol | 17.07.2018 | Closed
17.07.18 | .1. PPM | General | Amendments to PPM Scheduler | Iwan advised David to regular check the PPM Planner on Concerto for any changes. | Iwan/Nichol | On-going | On-going
17.07.18 | .5. EARLY WARNINGS | General | No action to report. |  |  | Closed | Closed
28.01.19 | .6. KPIs | General | To be submitted following completed PPM programme. | Iwan to monitor KPI's under the New Nichol contract for performance . UPDATE 14/11/2018 KPI figure for Sept 98%, Oct 100% Nov 100%, Dec 100%, January 100%, February 100%. Well done. UPDATE 12/03/2019 Iwan advise Nichol had achieved 100% for the months on January and February, Well done. UPDATE 21/05/2019 April KPI's 100% Well done | Iwan | 21.05.19 | Closed
17.07.18 | .7. CONTRACTUAL | General | Encompassed has now been liquidated contract novated to Nichol. | Encompassed has now been liquidated contract novated to Nichol. Iwan advised that the mobilisation period has been passed | Iwan | 17.07.2018 | Closed
17.07.18 | .7. CONTRACTUAL | General | Asbestos Works via Kier | Tom Somerville from Kier advised that he would arrange a separate meeting to discuss the possibility of Nichols being added to the Kier Sub-Contractors list. As all Kier/WC planned work have now been actioned, a meeting to be arranged for September when the new list of works from WC becomes available. | Nichol/Kier | 17.07.2018 | Closed
17.07.18 | .7. CONTRACTUAL | General | New Nichol Contract | Iwan advised with Contract with Nichol 3 years + 1 + 1 | Nichol/Kier | 17.07.2018 | Closed
13.08.18 | .1. PPM | General | PPM Scheduler | Iwan advised 6 x PPM tasks were overdue as shown to Julie and David via the Concerto Dashboard. Julie advised these would be cleared by the end of the week as access had now been arranged with sites UPDATE 13/11/2018 Julie advised PPM works are now completed with the exception of the Grove School Trowbridge, works to be carried out 21st December due to access issues. UPDATE 12/03/2019 Nichols advised all new orders had now been raised via Concerto for 2019/2020 | Iwan/Nichol | 21.05.2019 | Closed
13.08.18 | .1. PPM | Redlands Chippenham | Redland Chippenham URN 00780 | Iwan confirmed the site had now been split on Concerto with required new Concerto orders being placed. | Iwan/Nichol | 13.08.2018 | Closed
13.08.18 | 10. SITE CHANGES | URN 00086 Block 00296 Rowdeford School Head Teacher Cottage | Rowdeford School - Head Teacher Cottage - this site is now a permanent Void | Iwan to advise actions required on site | Iwan | 13.08.2018 | Closed
13.08.18 | 10. SITE CHANGES | URN 01036 Derriads Respite Centre Chippenham | URN 01036 Derriads Respite Centre Chippenham. Void property from the 31st August 2018 | Iwan to advise actions required on site | Iwan | 13.08.2018 | Closed
13.08.18 | 10. SITE CHANGES | URN 00025 Christie Miller Leisure Centre | URN 00025 Christie Miller Leisure Centre , This site was closed to the general public on the 18/08/2018. This will become a void Property | Iwan to advise actions required on site | Iwan | 13.08.2018 | Closed
13.08.18 | 12. COMPLIMENTS | Stonehenge Secondary School | A compliment was received from Stonehenge School | A compliment was received from the Stonehenge School on the Engineers conduct, knowledge, and his interaction with the site. | Nichol | 13.08.18 | Closed
14.11.18 | .0. H&S | The Stonehenge School | Whilst Nichols contractors were on site several incidents were noted. All works were stopped until issues had been resolved. | David has advised a full internal investigation is now being carried out. David has dismissed 2 staff and Nichol Contract Manger Steve Walsh, is on re-restricted duties. He is also on a temporary suspension from any further WC contracts until the investigation has been completed. David to continue to liaise with Iwan and Andria Baker. Iwan advised all parties are to answers to the issues on site as communication via Kier and Nichol was not evident. David added his apologies for the inconvenience caused to be passed Andrea. Issue now resolved. Closed 29/01/19 | Nichol | Closed | Closed
14.11.18 | .2. REACTIVE | The Stonehenge School | WC Suzanne Gough running project with Nichol for installation of fibre optic cable. | Nichol to liaise with Suzanne as access for these work require removal of panelling | Nichol/Suzanne Gough | 14.11.2018 | Closed
14.11.18 | .2. REACTIVE | Bushton Farm | Removal works required. | Iwan advised Concerto order for this site works has now been cancelled, Issues on site have now been resolved as advised by Gabrielle Crump (WC) | Nichol/WC | 14.11.2018 | Closed
14.11.18 | .4. SUBMISSIONS | Various | WC Staff changes for Nichol submissions | Iwan advised James Evans who was dealing with Nichol submission has now left WC. WC are in the process of recruiting. However this not effect submission as Ben Atkinson will be handling them for the foreseeable future. 29/01/19 closed | WC/Nichol | Closed | Closed
14.11.18 | .5. EARLY WARNINGS | The Stonehenge School | Due to the issues at The Stonehenge School a early warning notice had to be given | Due to the issues at The Stonehenge School an early warning notice had to be given as instructed by Kevin Butcher. This follows photographic evidence supplied to WC. Now resolved 28/01/19 closed | KB/Iwan | Closed | Closed
14.11.18 | .7. CONTRACTUAL | General | Nichol to only carry out works as per agreed contract | Iwan advised Nichol to only fulfil Contract as agreed with WC- Nichol cannot be used direct for planned works. If works are via Kier the process is to be followed, that 3 tenders have to be received. Iwan advised Nichol need to be approved via WC as a Management Company for planned works | Nichol/WC | Closed | Closed
14.11.18 | .7. CONTRACTUAL | General | Planned works | David advised if Nichol receive any planned works, a site visit will be arranged prior to any works being carried out. Also David requested that if works are required via Nichol they should also be involved in any pre-start meetings. 28/01/19 Meeting at County Hall with Kier and Wayne Robson. Closed | Nichol/WC | Closed | Closed
14.11.18 | .7. CONTRACTUAL | General | Annual General Meeting | Iwan to arrange the annual general meeting with Nichol, Housing, FM. 29/01/19 Booked for 12th March 2019, now closed | Nichol/WC/Housing | Closed | Closed
14.11.18 | 10. SITE CHANGES | Traveller Sites | Traveller site in the process of being sold | Iwan advised some Traveller sites are in the process of being sold by WC. Iwan is liaising with WC's Tim Bruce. Once transactions have been completed Nichol will be informed to remove sites from PPM planner UPDATE 21/05/2019 The sale of Traveller Site is still ongoing, once any decision has been made Iwan will update accordingly. UPDATE 11/09/2019 Iwan advised x 2 sites has now been sold (Oaktree & Dairyhouse) with completion to be on the 18/09/2019. Iwan has amended the PPM scheduler accordingly. UPDATE 13/11/2019 Iwan advised no further information has been supplied regarding remaining sites. Iwan to inform Nichol when changes have been made to Scheduler if further sites are sold. | Iwan/Julie | 13.11.19 | Closed
14.11.18 | 12. COMPLIMENTS | Stonehenge Secondary School | A compliment was received from Stonehenge School | A compliment was received from the Stonehenge School caretaker on the Engineers conduct, knowledge, when surveying the site. | Nichol | 14.11.18 | Closed
14.11.18 | .0. H&S | Various | DBS | Iwan requested an up to date list of Nichol staff who have been DBS checked. Iwan also advised Nichol any sub-contactors used need to be WC approved and to also have DBS checks. 28/01/19 List received now closed. | Nichol | Closed | Closed
14.11.18 | .7. CONTRACTUAL | General | Specification template | David to send Iwan a copy of the ''specification template''. Iwan to also liaise with Thierry (Concerto) to see if this document can be added to the system. 28/01/19 Nothing further road, template not sufficient for scope of works. | Nichol/WC | Closed | Closed
14.11.18 | .1. PPM | General | Site plans | Julie advise the site plans received re Holbrook required amendments. Iwan requested Julie liaise direct with Peter Slatford (WC) | Nichol/WC | 11.11.18 | Closed
28.11.19 | .2. REACTIVE | Concerto approval on orders | Removal quotes supplied awaiting gateway approval | Removal quotes supplied awaiting gateway approval | WC/Nichol | 12.03.19 | Closed
28.01.19 | .3. HOUSING | Issue with work flow | Issue with survey flow for removals |  | Dave/Steve | 18.07.19 | Closed
12.03.19 | .0. H&S | Various | No issues to report | No issues to report | Nichol | Closed | Closed
12.03.19 | .3. HOUSING | General | Steve advised before Nichols enter, the site will be checked for hygiene following several issues. | Steve advised before Nichols enter, the site will be checked for hygiene following several issues. | Steve/Dave | 18.07.19 | Closed
12.03.19 | .3. HOUSING | General | PPM works to be added to the tracker and will be split into 3 phases. | PPM works to be added to the tracker and will be split into 3 phases. | Steve/Dave | 18.07.19 | Closed
12.03.19 | .3. HOUSING | General | Various re-active projects | Various re-active project including garages - sheltered schemes are still ongoing. To be discussed in separate meeting. | Steve/Dave | 18.07.19 | Closed
12.03.19 | .3. HOUSING | Surveys | Surveys | Steve advise 1234 surveys had been completed with approx. 260 still outstanding. Most of these had been due to access problems. Steve to investigate and will advise Nichols accordingly | Steve/Dave | 18.07.19 | Closed
12.03.19 | .7. CONTRACTUAL | General | Contractual changes | Kevin advised any changes/issue to the contract are required to be documented to Iwan by the end of September 2019. Kevin will then liaise with procurement so that they are in place when contract is up for renewal/extended. | Nichol/WC | 21.05.19 | Closed
12.03.19 | .9. CAPITAL WORKS | General | Engaging Nichols with CMA works | Iwan advised that he had spoken to Wayne regarding engaging Nichols in any CMA works but as yet nothing had been decided. Kevin confirmed that more works will be going to tender and not automatically going to Kier with further contractors being potential added for CMA works. Kevin also advised any given works the relevant contractor should be in on all the pre-start meeting. | WC/Nichol | 21.05.19 | Closed
12.03.19 | 12. COMPLIMENTS | General | General | Kevin congratulated Nichols on their achievements after taking on a difficult task from previous contractor | KB/Nichol | 12.03.19 | Closed
21.05.19 | .0. H&S | Various | No issues to report | No issues to report | Nichol | Closed | Closed
21.05.19 | .1. PPM | PPM | PPM Scheduled works | Julie advised as agreed with Iwan PPM works have been adjusted so that Nichol can now manage the workflow with PPM works moved from July to June etc. | Nichol/WC | Closed | Closed
21.05.19 | .3. HOUSING | Surveys | Surveys | Dave advised there were still work stream issues covering, outstanding works an required new orders. Iwan advised he would liaise with Kevin and Housing to see if issue could be resolved. This could as be a result of several members of the team leaving. | Iwan/Kevin | Closed | Closed
21.05.19 | .4. SUBMISSIONS | Various | Submission payments | Iwan advised Nichol that they were contracted to be paid 28 days from once the invoice has been submitted to SAP. To try to have a continue cash flow, Julie will try to submit application fortnightly on a certain day so Mo can then allocate time aside to deal with Nichol application and create Cert. | Mo/Julie | 18.07.19 | Closed
21.05.19 | .4. SUBMISSIONS | Various | Submission | Iwan advised Nichol that PW needs to be named correctly as per Concerto as it had been noted PW was being received incorrectly named with reference to 02 & 03. Julie will investigate and advise appropriate staff accordingly, | Julie/Iwan | 18.07.19 | Closed
18.07.19 | .1. PPM | PPM | Remedials required from PPM Service | Iwan advised Julie when remedials are required from Service it has to be completed via Concerto and not by e-mail. By entering details via Concerto there is more of a trail and accountability. Julie to now follow this process and will contact Paula if training is required. 11/09/2019 Iwan advised remedials were now being correctly uploaded onto Concerto. | Julie | 11.09.19 | Closed
18.07.19 | .2. REACTIVE | General | Waste Notes | Iwan advised that waste notes supplied by Catharine, now need to be uploaded direct on Concerto and the relevant site. Iwan advised he had a back log that needed to still be added to Concerto. Julie confirmed she will now take on this process. 11/09/2019 Iwan advised that on some waste note the sites were not being identified so cannot be uploaded onto Concerto, Dave to liaise with Julie. | Julie | 13.11.19 | Closed
18.07.19 | 13.AOB | Surveys | Warminster Depot site including x 2 house and Bungalow | Warminster Depot site including x 2 house and Bungalow. Nichol attended site to carry out survey, to find for the bungalow wrong keys had been supplied and the houses had been vandalised and boarded up. Julie to now liaise with Bournehill and will re-arrange access. 11/09/2019 Works have now been completed. | Julie/WC | 11.09.19 | Closed
18.07.19 | 13.AOB | Durrington Swimming Pool | Durrington Swimming Pool - Survey | Dave advised they had attended site and completed a survey in July to then be informed an independent survey had also been completed by another contractor in July. Iwan advised Dave if works have been given to Kier they are the point of contact and WC have no control over a 3rd party. This issue had also been raised at a WC team meeting. Iwan to raise this issue again with Kevin about 3rd party contractors being used. 11.09.19 Iwan advised the issue of using a 3rd party had now been resolved and processes now agreed with Andrea and Wayne regarding any project works that require an Asbestos contractor. | Iwan/Kevin | 11.09.19 | Closed
18.07.19 | 13.AOB | Marlborough Resource Centre | Marlborough Resource Centre - Demolition Asbestos Survey | An order had been raised on Concerto 44570 for Nichols to attend and undertake a demolition asbestos survey. When on site sharps were discovered and works suspended. As yet Dave has not received an update from Bill Thielen (Project Manager). Iwan has advised Dave to have costs sent to Bill for the removal of the sharps so that the survey can be completed. 11.09.19 Works have now been completed. | Dave/Bill Thielen | 11.09.19 | Closed
11.09.19 | .3. HOUSING | Surveys | Surveys | Dave advised there were still work stream issues covering, outstanding works that required new orders. Iwan requested that both him and Kevin are invited to the next Housing Contractors meeting. UPDATE 13/11/2019 Dave advised that a meeting has been arranged on the 26/11/2019 to discuss outstanding issues. Iwan requested an update from the meeting. Iwan advised he would also be happy to attend the meeting if required, | Iwan/Kevin/Housing | 13.11.19 | Closed
11.09.19 | .6. KPIs | General | KPI's | 100% for both July and August Well done | Iwan | 11.09.19 | Closed
11.09.19 | 12. COMPLIMENTS | County Hall | County Hall | Iwan complimented Dave on their quick response to the situation at County Hall. | Iwan | 11.09.19 | Closed
11.09.19 | .4. SUBMISSIONS | Various | Submission | Mo advised Dave that 5 items were still sat in the disputed tab waiting to be re-submitted. Dave to liaise with Julie as she needs to action via the supplier portal. | Julie | 11.09.19 | Closed
11.09.19 | 13.AOB | General | Calculation of costs | Iwan enquired how costs where collated via removals etc. Dave advised they where benchmarked from information from other national contractors x 3. The same for waste disposal x 2 contactors. They then valuate themselves and their prices against common industries standards. This is to ensure competitiveness and to provide market tested prices for the WC Contract. | Iwan/Dave | 11.09.19 | Closed
13.11.19 | .2. REACTIVE | Surveys not completed | Surveys not completed on several site. Lypiatt Shops and Flats, Portemarsh Units. | Julie advised surveys had not completed on sites. Lypiatt Shops and Flats, & Portemarsh Units. Iwan advised these sites are under the remit of the Estates Team and until instructions have been received by them no action can be taken. Once estates authorise the works they can be added to next years schedule. UPDATE 14/01/2020 Iwan advised no further information had been supplied by The Estates Team, however in the future Management Surveys may be required. | Estates/Nichol | On-going | Open
13.11.19 | .2. REACTIVE | General | School floor removals | Regarding floor removal in schools. The issues raised is that the cost of the floor to be replaced after the removal of any tiles etc sits with the school so any remedials works and costs have to be approved by the School. Iwan to keep Nichol updated accordingly. | Iwan | 14.01.20 | Closed
13.11.19 | .5. EARLY WARNINGS | Housing | Dave advised there were still work stream issues within housing covering outstanding works and the required new orders. Iwan advised Dave to issue an Early Warning Notice to WC for not fulfilling the advised guaranteed works. | Dave advised there were still work stream issues within Housing covering outstanding works and the required new orders. Iwan advised Dave to issue an Early Warning Notice to WC for not fulfilling the advised guaranteed works. UPDATE 14/01/2020 Dave advised the issue was still ongoing regarding orders required from Housing. Iwan advised Dave to again raise an Early Warning Notice to WC for not fulfilling the advised guaranteed works as it would then have to be addressed. | Dave Nichol | On-going | Open
13.11.19 | .6. KPIs | General | KPI's | 100% for both Sept and Oct - Well done | Iwan | 12.11.19 | Closed
13.11.19 | .7. CONTRACTUAL | General | Contractual review of price increases from April 2020 | Iwan to have separate meeting with Dave to discuss price increases, when agreed figures have to be submitted to Cabinet by end of November 2019, agreed costs to be implemented from April 2020. Dave to advise Iwan of costs by W/E 15/11/2019, Iwan advised Dave that any removal works over £25,000.00 would now have to be procured and not just allocated to Nichol | Nichol/WC | 12.11.19 | Closed
13.11.19 | .9. CAPITAL WORKS | Melksham Library | Melksham Library - asbestos ceiling works | Melksham Library - asbestos ceiling works. Dave advised the ceiling works were still being monitored. Iwan requested a further update on the condition of the ceiling works. Update 14/01/2020 Iwan advised all works had now been completed. | Dave/Iwan | 14.01.20 | Closed
13.11.19 | .9. CAPITAL WORKS | Kingsbury Square Hostel | Kingsbury Square Hostel. The removal & disposal of asbestos | Kingsbury Square Hostel. The removal & disposal of asbestos. Dave advised all works have now been completed, | Nichol | 12.11.19 | Closed
14.01.20 | .0. H&S | Stonehenge School (Lower) | Stonehenge School (Lower) Loft clean | Stonehenge School (Lower) Loft clean. Dave advised due to the below ceiling being suspended there was a possible H & S risk to contactors when entering the loft space. Dean Nichol now acting as project manager and will work on a safe working process for persons working on site. | Nichol | 14.01.20 | Open
14.01.20 | .2. REACTIVE | Ashton Street Resource Centre (Void) | Ashton Street Resource Centre (Void) | Ashton Street Resource Centre (Void property) attendance to carry out a full R&D survey of the whole site for the purpose of demolition. Dean advised the site had some vandalised. Also bats have been discovered nesting on site. Andrea Baker to advise on the way forward. | Nichol/Andrea Baker | 14.01.20 | Open
14.01.20 | .2. REACTIVE | Old County Hall | Old County Hall Surfacing solution | Old County Hall - Surfacing solution. Dave advised that he was still waiting for an update from Steve French via Kier. | Nichol/Steve French | 14.01.20 | Open
14.01.20 | .6. KPIs | General | KPI's | 100% achieved. Well done | Iwan | 14.01.20
14.01.20 | .9. CAPITAL WORKS | General | Nichols - CMA works | CMA works - Iwan advised any CMA works required to be carried out during the summer relevant orders should be being raised before April | WC/Nichol | 14.01.20
14.01.20 | 13.AOB | Amesbury Sports Centre | Amesbury Sports Centre - Complete refurbishment | Amesbury Sports Centre - Complete site refurbishment. Iwan advised that a part survey could be required to be carried out. Iwan will keep Nichol updated accordingly. | Iwan/Dave | 14.01.20 | Open